## Verification Report
Planning Validation Report
Status | ✅ PASS
Timestamp | 2025-12-17T20:01:24.377Z
Stats
Total Assignments | 0
Valid Assignments | 0
Invalid Assignments | 0
Constraint Checks | Status | Violations
Hard: Min Workers | PASS | 0
Hard: Max Workers | PASS | 0
Hard: Skills | PASS | 0
Hard: Dependencies | PASS | 0
Hard: Double Booking | PASS | 0

## Completion Status
Task | TaskId | DoneHours | TotalHours | Progress | Status
Wall Batt insulation | t_1 | 0.00 | 5.00 | 0% | 🛑 Not Started
Baffels and Blown In Insulation | t_2 | 0.00 | 5.50 | 0% | 🛑 Not Started
Ceiling Rim Insulation | t_3 | 0.00 | 4.00 | 0% | 🛑 Not Started
Complete Drywall Back Panel | t_4 | 0.00 | 13.50 | 0% | 🛑 Not Started
Complete Exterior OSB | t_5 | 0.00 | 20.00 | 0% | 🛑 Not Started
Complete Roof 5/8 OSB | t_6 | 0.00 | 13.00 | 0% | 🛑 Not Started
Complete Exterior Fire Wall | t_7 | 0.00 | 10.00 | 0% | 🛑 Not Started
Interior Tape / Mud 1st Coat | t_8 | 0.00 | 33.00 | 0% | 🛑 Not Started
Interior Tape / Mud 2nd Coat | t_9 | 0.00 | 16.00 | 0% | 🛑 Not Started
Complete Exterior R-Max | t_10 | 0.00 | 10.50 | 0% | 🛑 Not Started
Final sand of drywall | t_11 | 0.00 | 2.00 | 0% | 🛑 Not Started
Tape and install windows | t_12 | 0.00 | 5.25 | 0% | 🛑 Not Started

## Idle Workers
Worker | Start | End
w_1 | 2024-01-01T07:00:00.000Z | 2024-01-01T17:00:00.000Z
w_10 | 2024-01-01T07:00:00.000Z | 2024-01-01T17:00:00.000Z
w_11 | 2024-01-01T07:00:00.000Z | 2024-01-01T17:00:00.000Z
w_12 | 2024-01-01T07:00:00.000Z | 2024-01-01T17:00:00.000Z
w_13 | 2024-01-01T07:00:00.000Z | 2024-01-01T17:00:00.000Z
w_14 | 2024-01-01T07:00:00.000Z | 2024-01-01T17:00:00.000Z
w_15 | 2024-01-01T07:00:00.000Z | 2024-01-01T17:00:00.000Z
w_16 | 2024-01-01T07:00:00.000Z | 2024-01-01T17:00:00.000Z
w_2 | 2024-01-01T07:00:00.000Z | 2024-01-01T17:00:00.000Z
w_3 | 2024-01-01T07:00:00.000Z | 2024-01-01T17:00:00.000Z
w_4 | 2024-01-01T07:00:00.000Z | 2024-01-01T17:00:00.000Z
w_5 | 2024-01-01T07:00:00.000Z | 2024-01-01T17:00:00.000Z
w_6 | 2024-01-01T07:00:00.000Z | 2024-01-01T17:00:00.000Z
w_7 | 2024-01-01T07:00:00.000Z | 2024-01-01T17:00:00.000Z
w_8 | 2024-01-01T07:00:00.000Z | 2024-01-01T17:00:00.000Z
w_9 | 2024-01-01T07:00:00.000Z | 2024-01-01T17:00:00.000Z