## Verification Report
Planning Validation Report
Status | ✅ PASS
Timestamp | 2025-12-13T02:12:59.787Z
Stats
Total Assignments | 11
Valid Assignments | 11
Invalid Assignments | 0
Constraint Checks | Status | Violations
Hard: Min Workers | PASS | 0
Hard: Max Workers | PASS | 0
Hard: Skills | PASS | 0
Hard: Dependencies | PASS | 0
Hard: Double Booking | PASS | 0

## Assignments
Task | TaskId | Worker | Start | End
Interior Tape / Mud 1st Coat | t3 | w1 | 2024-01-01T08:00:00.000Z | 2024-01-01T14:30:00.000Z
Interior Tape / Mud 1st Coat | t3 | w2 | 2024-01-01T08:00:00.000Z | 2024-01-01T14:30:00.000Z
Interior Tape / Mud 1st Coat | t3 | w4 | 2024-01-01T08:00:00.000Z | 2024-01-01T15:00:00.000Z
Interior Tape / Mud 1st Coat | t3 | w5 | 2024-01-01T08:00:00.000Z | 2024-01-01T14:30:00.000Z
Interior Tape / Mud 1st Coat | t3 | w6 | 2024-01-01T08:00:00.000Z | 2024-01-01T14:30:00.000Z
Interior Tape / Mud 2nd Coat | t4 | w1 | 2024-01-01T15:00:00.000Z | 2024-01-01T17:00:00.000Z
Interior Tape / Mud 2nd Coat | t4 | w2 | 2024-01-01T15:00:00.000Z | 2024-01-01T17:00:00.000Z
Interior Tape / Mud 2nd Coat | t4 | w4 | 2024-01-01T15:00:00.000Z | 2024-01-01T17:00:00.000Z
Interior Tape / Mud 2nd Coat | t4 | w5 | 2024-01-01T15:00:00.000Z | 2024-01-01T17:00:00.000Z
Interior Tape / Mud 2nd Coat | t4 | w6 | 2024-01-01T15:00:00.000Z | 2024-01-01T17:00:00.000Z
Wall Batt insulation | t2 | w3 | 2024-01-01T08:00:00.000Z | 2024-01-01T13:00:00.000Z

## Completion Status
Task | TaskId | DoneHours | TotalHours | Progress | Status
Tape and install windows | t1 | 0.00 | 5.25 | 0% | 🛑 Not Started
Wall Batt insulation | t2 | 5.00 | 5.00 | 100% | ✅ Complete
Interior Tape / Mud 1st Coat | t3 | 33.00 | 33.00 | 100% | ✅ Complete
Interior Tape / Mud 2nd Coat | t4 | 10.00 | 16.00 | 63% | 🚧 In Progress

## Idle Workers
Worker | Start | End
w3 | 2024-01-01T13:00:00.000Z | 2024-01-01T17:00:00.000Z
w1 | 2024-01-01T14:30:00.000Z | 2024-01-01T15:00:00.000Z
w2 | 2024-01-01T14:30:00.000Z | 2024-01-01T15:00:00.000Z
w5 | 2024-01-01T14:30:00.000Z | 2024-01-01T15:00:00.000Z
w6 | 2024-01-01T14:30:00.000Z | 2024-01-01T15:00:00.000Z

## Task Idle Periods
Task | TaskId | Start | End
Tape and install windows | t1 | 2024-01-01T08:00:00.000Z | 2024-01-01T17:00:00.000Z