## Time Study List
Inspection Area A
TASK 1 |  | Time Test Notes |  |  | Time | Guys | Serial # | Water LIne PSI |  | squarFeetModule | output quantity
| Layout Floor System | Time to Complete Task 1 |  |  | 1.5 HRS | 4 | 51501 | DWV PSI |  | linearFeetExteriorWalls | task completion
| Attached Joist | [6 empty] | OSB Nail Inspection |  | linearFeetInteriorWalls
| Finalize Foam / 5/8" Drywall | [6 empty] | 2" Foam Blocks |  | countInteriorWalls
TASK 2 |  | Time Test Notes |  |  | Time | Guys | Serial # | Screws through LVL into Joist |  | countToilets
| Deck the Floor (Screw) | Time to Complete Task 1 |  |  | 4 HRS | 4 | 51501 |  |  | linearFeetCabinets
| Cut Access Panels | [8 empty] | countTubsShowers
| Snap Wall Lines | [8 empty] | countSinks
| Rack and Install Skates | [8 empty] | countInteriorDoors
Station 2 | [9 empty] | countWindows
TASK 1 |  | Time Test Notes |  |  | Time | Guys | Serial # |  |  | countExteriorDoors
| Layout Plumbing Fixtures | This Happens in All Upper and Lower Floor Boxes |  |  | 2 HRS 10 MIN | 1 | 51501 |  |  | squareFeetExteriorCloseUp
| Drill Fixtures Holes / Stub Down Pipes | [8 empty] | squareFeetRoofing
TASK 2 |  | Time Test Notes | [7 empty] | hasHvacDucting
| Assemble DWV / Test | This only happens in upper level boxes |  |  | Time | Guys | Serial # |  |  | countElectricalTerminals
| Assemble Water / Test | [8 empty] | linearFeetFirewall
[8 empty] | Note - need to build out Mill shop tasks and specs |  | countStairs
TASK 3 |  | Time Test Notes |  |  | Time | Guys | Serial # |  |  | linearFeetModule
| Layout Electrical Fixtures | Time to Complete Task 2 |  |  | 6 HRS | 1 | 51501 |  |  | countBathrooms
| Drill Holes | [8 empty] | squareFeetFlooring
| Pull Wire | [8 empty] | countSinksToiletsTubsShowers
| Install Connectors | [8 empty] | countDoorsWindows
Station 3 | [7 empty] | Inspection Area B |  | squareFeetSiding
TASK 1 |  | Time Test Notes |  |  | Time | Guys | Serial # |  |  | countDoors
| Layout Drywall | Have a pile of around 10 walls to build, and drywall preped on the bridge. Then let them build all to walls. We need to know the # of walls, how many linear feet of walls and how log it took for them to build all of them. |  |  | 5 HRS 30 MIN | 4 | 51501 |  |  | linearFeetMariageWall
Build Wall Sections (per section)
Layout Wall Sections
Square / Secure Drywall to Walls
Foam Wall
Cut out Windows / Doors
Station 4
TASK 1 |  | Time Test Notes |  |  | Time | Guys | Serial #
| 3 Exterior Walls | Have all wall built and in rack. Assemple Full box full of walls. We need to know how long and ALSO the # of walls AND the total linear Feet of walls |  |  | 8 HRS 30 MIN | 3 | 12002
Install Interior walls
Last Exterior Wall
Install Stairs
Cut Bottom Plate
Lag
Install Rock Wool fire seperation
Station 6
TASK 1 |  | Time Test Notes |  |  | Time | Guys | Serial #
| Complete Rough Plumbing | Commplete Rough Plumbing and test in Kitchen Box and also in Bedrom Box. We need to know what the s/n each test was completed. In
Plumbing Nail Plates
TASK 2 |  | Time Test Notes |  |  | Time | Guys | Serial #
| Cut Out / Install Boxes | Just installing all boxes time test. Need to also know the number of boxes installed.
Station 7
TASK 1 |  | Time Test Notes |  |  | Time | Guys | Serial #
| Layout Drwall | Need to get two Different Times - one for a ceiling build and one for a roof build. Need to know S/N of each test. Start by having all lumber pre-cut, drywall stocked on Bridge |  |  | 1 HRS | 4 | 12001
TASK 2 |  |  |  |  | Time | Guys | Serial #
| Build Ceiling |  |  |  | 2 HRS 45 MIN | 4 | 12001
TASK 3 |  |  |  |  | Time | Guys | Serial #
| Build Roof |  |  |  | 8 HRS | 4 | 12002
Station 8
TASK 1 |  | Time Test Notes |  |  | Time | Guys | Serial #
| Layout HVAC | Get time for SF or duplex box. This needs to include the cutting of the holes in the top/bottom of the walls for the risers (they typically like to do this in two stations. We need to also have all of the risers pre made. Then we need to do a test on the first apartment building. The team should include a framers to help cut holes / modify framing, and then build all the soffit blocking material. |  |  | 6 HRS | 1 | 11002
Modify any framing
Install Ducting
Complete Blocking for Soffit
TASK 2 |  | Time Test Notes |  |  | Time | Guys | Serial #
| Pull Wires | With Boxes already fulling installed, pull all wires |  |  | 8 HRS | 2 | 11002
Panel Make Up
Smerf Tube
Tasks are grouped togeather and need to be balacnes togeather as a group not as individual taks. They are grouped togeather in each station. To talk through
Station 9
TASK 1 |  | Time Test Notes |  |  | Time | Guys | Serial #
| 1st Mud Coat On Ceiling | 1 Guy to Put first coat and Tape on Ceiling |  |  | 2 HRS | 2 | 12002
Station 10
TASK 1 |  | Time Test Notes |  |  | Time | Guys | Serial #
| Top out Plumbing | Extend Plumbing Throgh Ceiling or Roof |  |  | 8 HRS | 2 | 12002
Test DWV
Furnance Exhaust Run to outisde
TASK 2 |  | Time Test Notes |  |  | Time | Guys | Serial #
| Dryer Vent Brought to outside | These run in soffits and attics. We need to run a time test for the SF and duplex Boxes. And then we need to run one for the apartments |  |  | 8 HRS | 3 | 11001
Fart Fans Brought to outside
Station 11
TASK 1 |  | Time Test Notes |  |  | Time | Guys | Serial #
| Wall Batt insulation | Time to install all wall batts - MAKE SEPARATE TASK?? | linearFeetExteriorWalls, linearFeetFirewall | output quantity | 1 HRS 40 MIN | 3 | 14004
Interior Sound Wall Batt Insulation
TASK 2 |  | Time Test Notes |  |  | Time | Guys | Serial #
| Baffels and Blown In Insulation | Time to install Baffels and Blown In | squareFeetRoofing | output quantity | 2 HRS 40 MIN | 2 | 14004
TASK 3 |  | Time Test Notes |  |  | Time | Guys | Serial #
| Ceiling Rim Insulation | Time to install all ceiling box rim insulation | linearFeetExteriorWalls | output quantity | 2 HRS | 2 | 14004
TASK 4 |  | Time Test Notes |  |  | Time | Guys | Serial #
| Complete Drywall Back Panel | Need Linear Feet of Back Panel installed in a give amout of time. | linearFeetInteriorWalls, countInteriorWalls | output quantity | 6 HRS 50 MIN | 2 | 14004
Station 12
TASK 1 |  | Time Test Notes |  |  | Time | Guys | Serial #
| Complete Exterior OSB | Time Test | linearFeetMariageWall, linearFeetExteriorWalls | output quantity | 10 HRS | 2 | 14003
TASK 2 |  | Time Test Notes |  |  | Time | Guys | Serial #
| Complete Roof 5/8" OSB | Time Test | squareFeetRoofing | output quantity | 6 HRS 30 MIIN | 4 | 14004
TASK 3 |  | Time Test Notes |  |  | Time | Guys | Serial #
| Complete Exterior Fire Wall | Time Test | linearFeetFirewall | output quantity | 5 HRS | 2 | 14003
TASK 1 |  | Time Test Notes |  |  | Time | Guys | Serial #
| Interior Tape / Mud 1st Coat | Time Test | linearFeetInteriorWalls, linearFeetExteriorWalls, countInteriorWalls | output quantity | 5 HRS 30 MIN | 6 | 14003
Doe we need a dry time Task? |  |  |  |  | 2 HRS
TASK 2 |  | Time Test Notes |  |  | Time | Guys | Serial #
| Interior Tape / Mud 2nd Coat | Time Test | linearFeetExteriorWalls, linearFeetInteriorWalls, countInteriorWalls | output quantity | 4 HRS | 4 | 14003
Dry time Task? |  |  |  |  | 8 HRS
Station 13
TASK 1 |  | Time Test Notes |  |  | Time | Guys | Serial #
| Complete Exterior R-Max | Time Test | countWindows, linearFeetExteriorWalls | output quantity | 5 HRS 15 MIN | 2 | 14002
TASK 2 |  | Time Test Notes |  |  | Time | Guys | Serial #
| Final Sand of Drywall | Time Test | linearFeetExteriorWalls, linearFeetInteriorWalls, countInteriorWalls, squarFeetModule | output quantity | 1 HRS | 2 | 14002
Cover all opening
TASK 3 |  | Time Test Notes |  |  | Time | Guys | Serial #
| Prep Machine / Materials | Time Test | linearFeetExteriorWalls, linearFeetInteriorWalls, countInteriorWalls, squarFeetModule, countWindows | output quantity | 1 HRS 20 MIN | 1 | 14002
Spray Texture
Clean Up
Dry Time Task? |  |  |  |  | 3 HRS
TASK 4 |  | Time Test Notes |  |  | Time | Guys | Serial #
| Spray Flat Paint | Time Test | linearFeetExteriorWalls, linearFeetInteriorWalls, countInteriorWalls, squarFeetModule | output quantity | 1 HRS | 1 | 14002
| Spray Semi-Gloss Paint | [6 empty] | lin feet interior | 0.16667 | 200 | 200 | 4
Station 14 | [7 empty] | lin feet exterior | 0.16667 | 100 | 100 | 4
TASK 1 |  | Time Test Notes |  |  | Time | Guys | Serial # | count interior | 0.5 | 4 | 6 | 18
| Window Tape | Timed test for 4-5 hours for 4 guys for how many wondows they install. | countWindows | output quantity | 1 HRS 45MIN | 3 | 14001 | sq fee | 0.16667 | 400 | 400 | 4
Install Windows
| Window foam | [8 empty] | 24 |  | 30
TASK 2 |  | Time Test Notes |  |  | Time | Guys | Serial #
| Kitchen and Bath Cabinets Install | Record Number of Cabinets and also LF of Cabinets | linearFeetCabinets | output quantity | 9 HRS 30 MIN | 2 | 14001
TASK 3 |  | Time Test Notes |  |  | Time | Guys | Serial #
| Receptacles Installed | Must record numer of items hooked up | countElectricalTerminals | output quantity | 3 HRS 30 MIN | 2 | 14002
Switches Installed
Lights Installed
Panel Trim Out
Complete Functionality Test
Station 15
TASK 1 |  | Time Test Notes |  |  | Time | Guys | Serial #
| Fascia Soffit | Must Record LF of Fascia Soffit Installed | ?? | output quantity | 3 HRS 30 MIN | 5 | 14002
TASK 2 |  | Time Test Notes |  |  | Time | Guys | Serial #
| Install Siding | Must Record Sqft of Sising Installed no subtrackign windows | squareFeetExteriorCloseUp | output quantity | 30 HRS 20 MIN | 4 | 13003
TASK 3 |  | Time Test Notes |  |  | Time | Guys | Serial #
| Flooring Install | Sqft of flooring Installed. | squareFeetFlooring | output quantity | 8 HRS 40 MIN | 1 | 13004
Station 16
TASK 1 |  | Time Test Notes |  |  | Time | Guys | Serial #
| Interior and Exterior Door Install | Number of Doors Installed - Probably run Test with 2 guys | countDoors | output quantity
TASK 2 |  | Time Test Notes |  |  | Time | Guys | Serial #
| Baseboard and Window / Door Casing Install | Linear Ft of Baseboard and # of Windows Recorded | ?? | output quantity
Prep For Paint of Baseboard / Trim
TASK 3 |  | Time Test Notes |  |  | Time | Guys | Serial #
| Caulking Siding | Sqft of Siding Preped - run with 3 guys | squareFeetExteriorCloseUp, countDoorsWindows | output quantity
Mask Doors / Windows - Paint Prep
Exterior Paint Prep
Station 17
TASK 1 |  | Time Test Notes |  |  | Time | Guys | Serial #
| Paint Exterior including Doors | 1 guy doing painting including set up | squareFeetExteriorCloseUp, countExteriorDoors | output quantity | 2 HRS 30 MIN | 1 | 13003
TASK 2 |  | Time Test Notes |  |  | Time | Guys | Serial #
| Interior Paint Prep | Number of Doors and Windows | countWindows, countDoors | output quantity | 5 HRS 30 MIN | 2 | 13004
Station 18
TASK 1 |  | Time Test Notes |  |  | Time | Guys | Serial #
| Drip Edge | Sqft of roofing installed | squareFeetRoofing | output quantity | 6 HRS | 6 | 13004
Underlayment
Shingles
TASK 2 |  | Time Test Notes |  |  | Time | Guys | Serial #
| Plumbing Trims | Number of Sinks / Toilets / Showers / Tubs | countSinksToiletsTubsShowers | output quantity | 2 HRS | 2 GUYS | 13004
Station 19
TASK 1 |  | Time Test Notes |  |  | Time | Guys | Serial #
| Ceiling Wrap Spacer | Length of Box, Number of Bathrooms / Sqft of Flooring | linearFeetModule | task completion | 7 HRS | 2 | 13003
Load Appliances / Ship Loose
Hardware Finishes (towel racks / Light Fixtures / Toliet Lids)
Wrapping Installed
Station 20
TASK 1 |  | Time Test Notes |  |  | Time | Guys | Serial #
| Complete any P-Traps | Number of Showers / Tubs | countTubsShowers | output quantity | 1 HRS | 1 | 13003
Fixture Test on Plumbing
TASK 2 |  | Time Test Notes |  |  | Time | Guys | Serial #
| Remove Skates / Drywall Repair | Length of Box | linearFeetModule | task completion | 4 HRS | 2 | 13003
Foam Insulation - Firewall
Fire Foam
Final Clean
Station 21
TASK 3 |  | Time Test Notes |  |  | Time | Guys | Serial #
| Move box outside to storage | Same amout per box |  | task completion | 1 HRS | 3 | 13003

## Task List In Josh Format
Station | Task # | Take Discription | Min Workers | Max Workers | Tie to Box Characteristic | Global Task # | Time for Task Group | Cross Function Skills That Can Complete Task (in order) | Unit Measre - Column g | Labor hours | Laborers | Notes | S/N #
1 | 1 | Layout Floor System | 2 | 6 | Length of Box | 1 |  | AB | 62' 6" | 1.5 HRS | TOTAL OF 4 GUYS, | NO ACCESS PANELS | 51501
1 | 1 | Attached Joist | 2 | 6
1 | 1 | Finalize Foam / 5/8" Drywall | 2 | 6
1 | 2 | Deck the Floor (Screw) | 2 | 6 | Length of Box | 2 |  | AB | 62' 6" | 4 HRS | TOTAL OF 4 GUYS | NO ACCESS PANELS | 51501
1 | 2 | Cut Access Panels | 2 | 6
1 | 2 | Snap Wall Lines | 2 | 6
1 | 2 | Rack and Install Skates | 2 | 6
2 | 1 | Layout Plumbing Fixtures | 1 | 3 | Upper/lower level box then Number of Plumbing Fixtures | 3 |  | D | LOWER LEVEL, 8 PLUMBERING FIXTURES | 2 HRS 10 MIN | TOTAL OF 1 GUY |  | 51501
2 | 1 | Drill Fixtures Holes / Stub Down Pipes | 1 | 3
2 | 2 | Assemble DWV / Test | 1 | 3 | [7 empty] | LOWER LEVEL WAS NOT NEEDED | 51501
2 | 2 | Assemble Water / Test | 1 | 3 | [7 empty] | LOWER LEVEL WAS NOT NEEDED
2 | 3 | Layout Electrical Fixtures | 1 | 3 | Number of J-Boxes | 4 |  | C | 27 J BOXES | 6 HRS |  | TOTAL OF 1 GUY | 51501
2 | 3 | Drill Holes | 1 | 3
2 | 3 | Pull Wire | 1 | 3
2 | 3 | Install Connectors | 1 | 3
3 | 1 | Layout Drywall | 3 | 6 | LF of Walls | 5 |  | AB | 60.92 LF | 5 HRS 30 MIN | TOTAL OF 4 GUY | 1 GUY BUILDING WALLS, 3 LAYING OUT | 51501
3 | 1 | Build Wall Sections (per section) | 3 | 6
3 | 1 | Layout Wall Sections | 3 | 6
3 | 1 | Square / Secure Drywall to Walls | 3 | 6
3 | 1 | Foam Wall | 3 | 6
3 | 1 | Cut out Windows / Doors | 3 | 6
4 | 1 | 3 Exterior Walls | 2 | 6 | LF of Walls or Number of Walls | 6 |  | AB | 221 LF , 21 WALLS | 8 HRS 30 MIN | TOTAL OF 3 GUYS |  | 12002
4 | 1 | Install Interior walls | 2 | 8
4 | 1 | Last Exterior Wall | 2 | 8
4 | 1 | Install Stairs | 2 | 8 | [7 empty] | NO STAIRS
4 | 1 | Cut Bottom Plate | 2 | 8
4 | 1 | Lag | 2 | 8
4 | 1 | Install Rock Wool fire seperation | 2 | 8
6 | 1 | Complete Rough Plumbing | 1 | 4 | Number of Plumbing Fixtures | 7 |  | D | 5 FIXTURES | 10 HRS 50 MIN | TOTAL OF 2 GUYS |  | 12001
6 | 1 | Plumbing Nail Plates | 1 | 4
6 | 2 | Cut Out / Install Boxes | 2 | 4 | Number of J Boxes | 8 |  | E | 34 BOXES 10 CEILING LIGHTS,1 ELECTRICAL PANEL | 14 HRS 55 MIN | TOTAL OF 2 GUYS |  | 12001
7 | 1 | Layout Drywall | 2 | 8 | Roof or Ceiling then Length of Box | 9 |  | AB | 45' 6" LNF, CEILING | 1 HRS | TOTAL OF 4 GUYS |  | 12001
7 | 2 | Building Ceiling | 2 | 8 |  |  |  |  | CEILING | 2HRS 45 MIN | TOTAL OF 4 GUYS |  | 12001
7 | 3 | Build Roof | 2 | 8 |  |  |  |  | ROOF | 8 HRS | TOTAL OF 4 GUYS |  | 12002
8 | 1 | Layout HVAC | 2 | 6 | LF of HVAC Ducting | 10 |  | MAB | 37 LF | 6 HRS | TOTAL OF 1 GUYS | LF DOES NOT TAKE INTO ACCOUNT FANS, DRYER, FURNANCE EXHUAST | 11002
8 | 1 | Modify any framing | 2 | 6
8 | 1 | Install Ducting | 2 | 6
8 | 1 | Complete Blocking for Soffit | 2 | 6
8 | 2 | Pull Wires | 2 | 4 | Number of J Boxes | 11 |  | E | 37 J BOXES, 10 CEILING LIGHTS, 2 BATH ROOM FANS | 8 HRS | TOTAL OF 2 GUYS |  | 11002
8 | 2 | Panel Make Up | 2 | 4 | [7 empty] | NO PANEL 2ND FLOOR
8 | 2 | Smerf Tube | 2 | 4
9 | 1 | 1st Coat of Mud on Ceiling | 1 | 2 | Sqft of Box | 12 |  | F | 720 SQFT | 2 HRS | TOTAL OF 2 GUYS |  | 12002
10 | 1 | Top out Plumbing | 2 | 4 | Number of Plumbing Fixtures | 13 |  | D | 7 PLUMBING FIXTURES | 8 HRS | TOTAL OF 2 GUYS |  | 12002
10 | 1 | Test DWV | 2 | 4 |  |  |  | D
10 | 2 | Dryer Vent Brought to outside | 1 | 4 | LF of Ducting |  |  |  | 105 LF OF RISERS, 3 LF OF DUCT EXHUAST FAN | 8 HRS | TOTAL OF 3 GUYS | NO DRYER VENT, 9 HOLES FOR BOOTS | 11001
10 | 2 | Fart Fans Brought to outside | 1 | 4 |  |  |  |  | 1 FAN
10 | 2 | Furnance Exhaust Run to outisde | 1 | 4 | [7 empty] | NO FURNANCE VENT
11 | 1 | Wall Batt insulation | 2 | 6 | LF of Exterior Walls + LF of Sound Walls | 14 |  | ABEFGIJ | 126 LF | 1 HRS 40 MIN | TOTAL OF 3 GUYS |  | 14004
11 | 1 | Interior Sound Walls Batt Insulation | 2 | 6 | Interior sound wall batt insulation |  |  |  | 49 LF |  |  |  | 14004
11 | 2 | Baffels and Blown-in Insulation | 2 | 6 | Roof Yes/No then LF of Exterior Walls | 15 |  | ABEFGIJ | 77 LF | 2 HRS 40 MIN | TOTAL OF 2 GUYS |  | 14004
11 | 3 | Ceiling and Rim Joist | 2 | 6 | Roof Yes/No then Sqft of Box | 16 |  | ABEFGIJ | 686 SQFT | 2 HRS | TOTAL OF 2 GUYS |  | 14004
11 | 4 | Complete Drywall Back Panel | 2 | 6 | 1/2 LF of Interior Walls | 17 |  | EABFGHIJ |  | 6 HRS 50 MIN | TOTAL OF 2 GUYS |  | 14004
12 | 1 | Complete Exterior OSB | 2 | 8 | Full Wall Perimeter LF | 18 |  | ABI |  | 10 HRS | TOTAL OF 2 GUYS |  | 14003
12 | 2 | Complete Roof 5/8" OSB | 2 | 8 | Roof or Ceiling then Length of Box | 19 |  | ABI | ROOF- 49 LF | 6 HRS 30 MIN | TOTAL OF 4 GUYS |  | 14004
12 | 3 | Complete Exterior Fire Wall | 2 | 8 | Fire Wall Yes/No then LF of Exterior Fire Wall | 20 |  | AEF | FIREWALL-49 LF | 5 HRS | TOTAL OF 2 GUYS |  | 14003
12 | 4 | Interior Tape / Mud 1st Coat | 2 | 8 | LF of all Walls | 21 |  | F |  | 5HRS 30 MIN | TOTAL OF 6 GUYS |  | 14003
12 | 5 | Dry Time First Coat | 0 | 0 | How to account for over night | 22 |  |  |  | 2 HRS |  | DOES NOT REQUIRE LABOR FOR DRYING | 14003
12 | 6 | Interior Tape / Mud 2nd Coat | 2 | 8 | LF of all Walls | 23 |  | F |  | 4 HRS | TOTAL OF 4 GUYS |  | 14003
12 | 7 | Dry Time 2nd Coat | 0 | 0 | How to account for over night | 24 |  |  |  | 8 HRS |  | DOES NOT REQUIRE LABOR FOR DRYING | 14003
13 | 1 | Complete Exterior R-Max | 2 | 8 | LF of Exterior Walls | 25 |  | ABEFGHIJ |  | 5 HRS 15 MIN | TOTAL OF 2 GUYS |  | 14002
13 | 2 | Final Sand of Drywall | 2 | 6 | LF of all walls | 26 |  | FAB |  | 1 HRS | TOTAL OF 2 GUYS |  | 14002
13 | 2 | Cover all opening | 2 | 6 |  | 27 |  | ABDEFGHIJL
13 | 3 | Prep Machine / Materials | 2 | 6 | LF of all walls | 28 |  | G |  | 1HRS 20 MIN | TOTAL OF 1 GUYS |  | 14002
13 | 3 | Spray Texture | 2 | 2
13 | 3 | Clean Up | 2 | 2
13 | 3 | Dry Time | 0 | 0 | [5 empty] | 3 HRS |  | DOES NOT REQUIRE LABOR FOR DRYING
13 | 4 | Spray Flat Paint | 1 | 1 | LF of All Walls | 29 |  | H |  | 1 HRS | TOTAL OF 1 GUYS |  | 14002
13 | 4 | Spray Semi-Gloss Paint | 1 | 1
14 | 1 | Window Tape | 2 | 6 | # of Windows | 30 |  | AB | 4 WINDOWS | 1 HRS 45 MIN | TOTAL OF 3 GUYS | INCLUDED 15 MIN INSPECTION TIME | 14001
14 | 1 | Install Windows | 2 | 6
14 | 1 | Window foam | 2 | 6
14 | 2 | Kitchen and Bath Cabinets Install | 2 | 6 | LF of Cabinets Including Uppers | 31 |  | BAJ |  | 9 HRS 30 MIN | TOTAL OF 2 GUYS | TOTAL TIME FOR BOTH SIDES | 14001
14 | 3 | Receptacles Installed | 1 | 3 | # of J-Boxes | 32 |  | C | 14 | 3 HRS 30 MIN | TOTAL OF 2 GUYS |  | 14002
14 | 3 | Switches Installed | 1 | 3 |  |  |  |  | 12
14 | 3 | Lights Installed | 1 | 3 |  |  |  |  | 12
14 | 3 | Panel Trim Out | 1 | 3 |  |  |  |  | NO PANEL
14 | 3 | Complete Functionality Test | 1 | 3 |  |  |  |  | 2 FANS AND 4 SMOKES
15 | 1 | Fascia Soffit | 2 | 6 | Roof Square Ft | 33 |  | ABIJ |  | 3 HRS 30 MIN | TOTAL OF 5 GUYS |  | 14002
15 | 2 | Install Siding | 2 | 6 | SF of Siding | 34 |  | ABJ |  | 3 HRS 20 MIN | TOTAL OF 4 GUYS |  | 13003
15 | 3 | Flooring Install | 1 | 4 | Sqft of Vynil Flooring | 35 |  | JB |  | 8 HRS 40 MIN | TOTAL OF 1 GUYS |  | 13004
16 | 1 | Interior and Exterior Door Install | 2 | 6 | # of Doors | 36 |  | BAJ | [5 empty] | STILL TRYING TO GET DATA FOR STATION 16. ISSUES WITH DOORS NOT BEING IN STOCK
16 | 2 | Baseboard and Window / Door Casing Install | 2 | 6 | # of Interior Doors + LF of Interior Walls | 37 |  | BAJ
16 | 3 | Prep For Paint of Baseboard / Trim | 1 | 4 | # of Interior Doors + LF of Interior Walls | 38 |  | HBGBJ
16 | 4 | Caulking Siding | 1 | 6 | Siding SF | 39 |  | HABJ
16 | 4 | Mask Doors / Windows - Paint Prep | 1 | 6
16 | 4 | Exterior Paint Prep | 1 | 6
17 | 1 | Paint Exterior including Doors | 2 | 2 | SF of Siding + Exterior Doors | 40 |  | H |  | 2 HRS 30 MIN | TOTAL OF 1 GUYS | 1 HR OF DRYING TIME NOT INCLUDED IN TOTAL TIME | 13003
17 | 2 | Interior Paint Prep | 1 | 6 | LF of all Walls + Number of Windows and Doors | 41 |  | HBGBJ | 6 DOORS, 6 WINDOWS | 5 HRS 30 MIN | TOTAL OF 2 GUYS |  | 13004
18 | 1 | Drip Edge | 1 | 6 | SF of Roofing | 42 |  | IA |  | 6 HRS | TOTAL OF 6 GUYS |  | 13004
18 | 1 | Underlayment | 1 | 6
18 | 1 | Shingles | 1 | 6
18 | 2 | Plumbing Trims | 1 | 4 | Number of Plumbing Fixtures | 43 |  | D | 8 PLUMBING FIXTURES | 2 HRS | TOTAL OF 2 GUYS |  | 13004
19 | 1 | Ceiling Wrap Spacer | 1 | 6 | Length of Box + 5x Number of Appliances | 44 |  | AB |  | 7 HRS | TOTAL OF 2 GUYS |  | 13003
19 | 1 | Load Appliances / Ship Loose | 1 | 6
19 | 1 | Hardware Finishes (towel racks / Light Fixtures / Toliet Lids) | 1 | 6
19 | 1 | Wrapping Installed | 1 | 6
20 | 1 | Complete any P-Traps | 1 | 6 | Number of Tubs and Showers | 45 |  | D |  | 1 HRS | TOTAL OF 1 GUYS |  | 13003
20 | 1 | Fixture Test on Plumbing | 1 | 6
20 | 2 | Remove Skates / Drywall Repair | 1 | 6 | Length of Box | 46 |  | AB |  | 4 HRS | TOTAL OF 2 GUYS |  | 13003
20 | 2 | Foam Insulation - Firewall | 1 | 6
20 | 2 | Fire Foam | 1 | 6
20 | 2 | Final Clean | 1 | 6
21 | 1 | Move Box to Outside Storage | 2 | 3 | Same time for all | 47 |  | K |  | 1 HRS | TOTAL OF 3 GUYS |  | 13003

## Box Charcteristics
Need to update theee to account for 0's for things like rooding and blow in insulation
Serial Number | Length | Width | Square Feet | Number of Plumbing Fixtrures | Number of J-Boxes | LF Exterior Walls | LF of Exterior Fire Wall | LF of Interior Walls | Number of Interior Walls | LF of Interior Fire / Sound Walls | LF of Ducting | LF of Cabinets Including Uppers | Roof Sqft | LF of Fascia | Siding Sqft | Number of Doors | Number of Windows | Sqft of Vynyl Flooring Installed | Number of Appliances | Number of Tubs/Showers

## Labor Ratios
Global Task # | SN of Study | Time Study (hours) | Number of Workers | Linked To Characteristic | Value of Characteristic | Ratio of Characteristic Per Hour
1 | 2503001 | 3.3 | 3 | Length of Box | 70.5 | 7.1212 | This is an Example
2 |  | 7 | 4 | Roof square footage | 800 | 28.5714
3 |  |  |  |  | 0 | 0
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44

## Cross Functional Skills
Need to update these to break down into items under same trade
| Labor Type |  |  |  | A | B | C | V | D | E | F | G | H | I | J | K | L | M
| Employee | Home Station | Primary Skill | Lead | Framing | Finish Carpentry | Electrical Trim | Electrical Rough | Plumbing | Drywall Hanging | Drywall Mud | Textrure | Painting | Roofing | Flooring | Box Moving | Cuttinng | HVAC
Example | Jose Lousie | 4 | A | X | A: 1; Need to update these to break down into items under same trade B: 3; Need to update these to break down into items under same trade C: 4; Need to update these to break down into items under same trade V: X; Need to update these to break down into items under same trade E: 2; Need to update these to break down into items under same trade I: 5; Need to update these to break down into items under same trade L: 6
Example | Juan Carlos | 16 | J |  | Need to update these to break down into items under same trade B: X; Need to update these to break down into items under same trade C: 1; Need to update these to break down into items under same trade V: 2; Need to update these to break down into items under same trade E: X; Need to update these to break down into items under same trade J: X
Test 3
Teat 4
1