## Module attributes
INSERT
| SKILLS | ID HERE |  | MODULE ATTRIBUTES
A | Framing |  | 1 | Length
B | Electrical Rough |  | 2 | Width
C | Plumbing Rough |  | 3 | Square Feet
D | HVAC |  | 4 | LF of Cabinets Including Uppers
E | Drywall Hanging |  | 5 | Number of Doors
F | Drywall Mud |  | 6 | Number of Windows
G | Texture |  | 7 | Sqft of Vynyl Flooring Installed
H | Finish Carpentry |  | 8 | Sqft of Carpet
I | Painting |  | 9 | Number of J-Boxes
J | Electrical Trim |  | 10 | Number of Plumbing Fixtures
K | Plumbing Trim |  | 11 | Number of Tubs/Showers
L | Roofing |  | 12 | LF Exterior Walls
M | Flooring |  | 13 | LF of Exterior Fire Wall
N | Box Moving |  | 14 | LF of Interior Walls
O | Pre assembly |  | 15 | Number of Interior Walls
P | General Labor |  | 16 | LF of Interior Fire Wall
|  |  | 17 | LF of Interior Sound Wall
|  |  | 18 | Total LF of All Walls
|  |  | 19 | Number of Mini Splits
|  |  | 20 | Number of Furance
|  |  | 21 | LF of Ducting
|  |  | 22 | Number of Appliances
|  |  | 23 | Roof Square Ft
|  |  | 24 | Sqft Roof Underlayment
|  |  | 25 | Sqft of Finished Roofing
|  |  | 26 | LF of Fascia
|  |  | 27 | Siding Installed Sqft
|  |  | 28 | Number of Sinks
|  |  | 29 | Number of Stair Sections

## Departments and skills
|  | SKILLS | [15 empty] | DEPARTMENTS
|  | A | B | C | D | E | F | G | H | I | J | K | L | M | N | O | P
| Employee | Framing | Electrical Rough | Plumbing Rough | HVAC | Drywall Hanging | Drywall Mud | Texture | Finish Carpentry | Painting | Electrical Trim | Plumbing Trim | Roofing | Flooring | Box Moving | Pre assembly | General Labor | Preassembly | Structure | MEP | Building Envelope | Interior / Exterior | MEP Finish | Final Close-Out / Wrap
Example | Jose Lousie | SKILLS A: 1; SKILLS B: 4; SKILLS E: 2; SKILLS H: 3; SKILLS J: X; SKILLS L: 5; SKILLS O: 6
Example | Juan Carlos | SKILLS B: 1; SKILLS E: X; SKILLS H: X; SKILLS J: 2; SKILLS M: X
Test 3
Teat 4

## Module Profile Data
MODULE ATTRIBUTES -->
|  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29
Project | Profile | Serial Number | Saw Box | Length | Width | Square Feet | LF of Cabinets Including Uppers | Number of Doors | Number of Windows | Sqft of Vynyl Flooring Installed | Sqft of Carpet | Number of J-Boxes | Number of Plumbing Fixtures | Number of Tubs/Showers | LF Exterior Walls | LF of Exterior Fire Wall | LF of Interior Walls | Number of Interior Walls | LF of Interior Fire Wall | LF of Interior Sound Wall | Total LF of All Walls | Number of Mini Splits | Number of Furances | LF of Ducting | Number of Appliances | Roof Square Ft | Sqft Roof Underlayment | Sqft of Finished Roofing | LF of Fascia | Siding Installed Sqft | Number of Sinks | Number of Stair Sections
Thelcrest | Duplex 1 A-A 1st floor | 2601-01 | x | 29 | 16 | 464 | 28 | 4 | 3 | 464 | 0 | 45 | 5 | 0 | 90 | 16 | 28 | 5 | 29 | 29 | 118 | 1 | 0 | 45 | 5 | 0 | 0 | 0 | 0 | 840 | 2 | 1
Thelcrest | Duplex 1 B-B 2nd floot | 2601-02 | x | 29 | 16 | 464 | 3 | 5 | 5 | 0 | 464 | 34 | 4 | 1 | 90 | 45 | 46 | 8 | 0 | 0 | 136 | 1 | 0 | 15 | 2 | 960 | 960 | 960 | 90 |  | 1 | 1
Thelcrest | Duplex 1 C-C studio | 2601-03 | x | 29 | 16 | 464 | 28 | 5 | 5 | 464 | 0 | 45 | 6 | 1 | 90 | 45 | 31 | 8 | 29 | 29 | 121 | 1 | 0 | 13 | 7 | 960 | 960 | 960 | 184 | 471 | 2 | 0
Thelcrest | Duplex 1 A-A 1st floor | 2602-01 | x | 29 | 16 | 464 | 28 | 4 | 3 | 464 | 0 | 45 | 5 | 0 | 90 | 16 | 28 | 5 | 29 | 29 | 118 | 1 | 0 | 45 | 5 | 0 | 0 | 0 | 0 | 840 | 2 | 1
Thelcrest | Duplex 1 B-B 2nd floor | 2602-02 | x | 29 | 16 | 464 | 3 | 5 | 5 | 0 | 464 | 34 | 4 | 1 | 90 | 45 | 46 | 8 | 0 | 0 | 136 | 1 | 0 | 15 | 2 | 960 | 960 | 960 | 90 |  | 1 | 1
Thelcrest | Duplex 1 C-C studio | 2602-03 | x | 29 | 16 | 464 | 28 | 5 | 5 | 464 | 0 | 45 | 6 | 1 | 90 | 45 | 31 | 8 | 29 | 29 | 121 | 1 | 0 | 13 | 7 | 960 | 960 | 960 | 184 | 471 | 2 | 0
Crossing | Bldg A | 2603-A01 | x | 35 | 13 | 455 | 3 | 8 | 2 | 455 | 0 | 35 | 4 | 1 | 96 | 13 | 61 | 10 | 13 | 13 | 157 | 2 | 1 | 20 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0
Crossing | Bldg A | 2603-A02 | x | 35 | 13 | 455 | 40 | 2 | 1 | 455 | 0 | 33 | 2 | 0 | 96 | 13 | 0 | 0 | 35 | 35 | 96 | 1 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0
Crossing | Bldg A | 2603-A03 | x | 35 | 13 | 455 | 40 | 2 | 1 | 455 | 0 | 33 | 2 | 0 | 96 | 13 | 0 | 0 | 35 | 35 | 96 | 1 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0
Crossing | Bldg A | 2603-A04 | x | 30 | 13 | 390 | 3 | 7 | 5 | 390 | 0 | 28 | 4 | 1 | 86 | 0 | 45 | 9 | 0 | 0 | 131 | 2 | 1 | 20 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0
Crossing | Bldg A | 2603-A05 | x | 30 | 13 | 390 | 3 | 6 | 3 | 390 | 0 | 28 | 4 | 1 | 86 | 13 | 61 | 10 | 13 | 13 | 147 | 2 | 1 | 20 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0
Crossing | Bldg A | 2603-A06 | x | 35 | 13 | 455 | 40 | 2 | 1 | 455 | 0 | 33 | 2 | 0 | 96 | 13 | 0 | 0 | 35 | 35 | 96 | 1 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0
Crossing | Bldg A | 2603-A07 | x | 35 | 13 | 455 | 40 | 2 | 1 | 455 | 0 | 33 | 2 | 0 | 96 | 13 | 0 | 0 | 35 | 35 | 96 | 1 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0
Crossing | Bldg A | 2603-A08 | x | 30 | 13 | 390 | 3 | 7 | 5 | 390 | 0 | 28 | 4 | 1 | 86 | 0 | 45 | 9 | 0 | 0 | 131 | 2 | 1 | 20 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0
Crossing | Bldg A | 2603-A09 | x | 30 | 13 | 390 | 3 | 6 | 3 | 390 | 0 | 28 | 4 | 1 | 86 | 13 | 61 | 10 | 13 | 13 | 147 | 2 | 1 | 20 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0
Crossing | Bldg A | 2603-A10 | x | 35 | 13 | 455 | 40 | 2 | 1 | 455 | 0 | 33 | 2 | 0 | 96 | 13 | 0 | 0 | 35 | 35 | 96 | 1 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0
Crossing | Bldg A | 2603-A11 | x | 35 | 13 | 455 | 40 | 2 | 1 | 455 | 0 | 33 | 2 | 0 | 96 | 13 | 0 | 0 | 35 | 35 | 96 | 1 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0
Crossing | Bldg A | 2603-A12 | x | 30 | 13 | 390 | 3 | 7 | 5 | 390 | 0 | 28 | 4 | 1 | 86 | 0 | 45 | 9 | 0 | 0 | 131 | 2 | 1 | 20 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0
Crossing | Bldg B | 2604-B01 | x | 30 | 11 | 330 | 30 | 2 | 1 | 330 | 0 | 31 | 2 | 0 | 82 | 35 | 0 | 0 | 0 | 0 | 82 | 1 | 0 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0
Crossing | Bldg B | 2604-B02 | x | 34 | 11 | 374 | 6 | 4 | 2 | 374 | 0 | 23 | 5 | 1 | 82 | 0 | 30 | 7 | 30 | 30 | 112 | 1 | 1 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 0
Crossing | Bldg B | 2604-B03 | x | 30 | 11 | 330 | 3 | 4 | 2 | 330 | 0 | 21 | 4 | 1 | 82 | 0 | 31 | 7 | 30 | 30 | 113 | 1 | 1 | 21 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0
Crossing | Bldg B | 2604-B04 | x | 30 | 11 | 330 | 30 | 2 | 1 | 330 | 0 | 31 | 2 | 0 | 82 | 35 | 0 | 0 | 0 | 0 | 82 | 1 | 0 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0
Crossing | Bldg B | 2604-B05 | x | 30 | 11 | 330 | 30 | 2 | 1 | 330 | 0 | 31 | 2 | 0 | 82 | 35 | 0 | 0 | 0 | 0 | 82 | 1 | 0 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0
Crossing | Bldg B | 2604-B06 | x | 34 | 11 | 374 | 6 | 5 | 2 | 374 | 0 | 23 | 5 | 1 | 82 | 0 | 30 | 7 | 30 | 30 | 112 | 1 | 1 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 0
Crossing | Bldg B | 2604-B07 | x | 30 | 11 | 330 | 3 | 5 | 2 | 330 | 0 | 21 | 5 | 1 | 82 | 0 | 31 | 7 | 30 | 30 | 113 | 1 | 1 | 21 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 0
Crossing | Bldg B | 2604-B08 | x | 30 | 11 | 330 | 30 | 2 | 1 | 330 | 0 | 31 | 2 | 0 | 82 | 35 | 0 | 0 | 0 | 0 | 82 | 1 | 0 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0
Crossing | Bldg B | 2604-B09 | x | 30 | 11 | 330 | 30 | 2 | 1 | 330 | 0 | 31 | 2 | 0 | 82 | 35 | 0 | 0 | 0 | 0 | 82 | 1 | 0 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0
Crossing | Bldg B | 2604-B10 | x | 34 | 11 | 374 | 6 | 5 | 2 | 374 | 0 | 23 | 5 | 1 | 82 | 0 | 30 | 7 | 30 | 30 | 112 | 1 | 1 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 0
Crossing | Bldg B | 2604-B11 | x | 30 | 11 | 330 | 3 | 5 | 2 | 330 | 0 | 21 | 5 | 1 | 82 | 0 | 31 | 7 | 30 | 30 | 113 | 1 | 1 | 21 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 0
Crossing | Bldg B | 2604-B12 | x | 30 | 11 | 330 | 30 | 2 | 1 | 330 | 0 | 31 | 2 | 0 | 82 | 35 | 0 | 0 | 0 | 0 | 82 | 1 | 0 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0
Crossing | Bldg C | 2605-C01 | x | 35 | 13 | 455 | 32 | 1 | 2 | 455 | 0 | 32 | 2 | 0 | 96 | 35 | 0 | 0 | 0 | 0 | 96 | 1 | 1 | 7 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0
Crossing | Bldg C | 2605-C02 | x | 42 | 13 | 546 | 6 | 7 | 2 | 455 | 0 | 33 | 7 | 2 | 110 | 0 | 29 | 8 | 42 | 42 | 139 | 2 | 0 | 66 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 0
Crossing | Bldg C | 2605-C03 | x | 42 | 13 | 546 | 6 | 7 | 2 | 455 | 0 | 33 | 7 | 2 | 110 | 0 | 29 | 8 | 42 | 42 | 139 | 2 | 0 | 66 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 0
Crossing | Bldg C | 2605-C04 | x | 35 | 13 | 455 | 32 | 1 | 2 | 455 | 0 | 32 | 2 | 0 | 96 | 35 | 0 | 0 | 0 | 0 | 96 | 1 | 1 | 7 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0
Crossing | Bldg C | 2605-C05 | x | 35 | 13 | 455 | 32 | 1 | 2 | 455 | 0 | 32 | 2 | 0 | 96 | 35 | 0 | 0 | 0 | 0 | 96 | 1 | 1 | 7 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0
Crossing | Bldg C | 2605-C06 | x | 42 | 13 | 546 | 6 | 7 | 2 | 455 | 0 | 33 | 7 | 2 | 110 | 0 | 29 | 8 | 42 | 42 | 139 | 2 | 0 | 66 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 0
Crossing | Bldg C | 2605-C07 | x | 42 | 13 | 546 | 6 | 7 | 2 | 455 | 0 | 33 | 7 | 2 | 110 | 0 | 29 | 8 | 42 | 42 | 139 | 2 | 0 | 66 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 0
Crossing | Bldg C | 2605-C08 | x | 35 | 13 | 455 | 32 | 1 | 2 | 455 | 0 | 32 | 2 | 0 | 96 | 35 | 0 | 0 | 0 | 0 | 96 | 1 | 1 | 7 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0
Crossing | Bldg C | 2605-C09 | x | 35 | 13 | 455 | 32 | 1 | 2 | 455 | 0 | 32 | 2 | 0 | 96 | 35 | 0 | 0 | 0 | 0 | 96 | 1 | 1 | 7 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0
Crossing | Bldg C | 2605-C10 | x | 42 | 13 | 546 | 6 | 7 | 2 | 455 | 0 | 33 | 7 | 2 | 110 | 0 | 29 | 8 | 42 | 42 | 139 | 2 | 0 | 66 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 0
Crossing | Bldg C | 2605-C11 | x | 42 | 13 | 546 | 6 | 7 | 2 | 455 | 0 | 33 | 7 | 2 | 110 | 0 | 29 | 8 | 42 | 42 | 139 | 2 | 0 | 66 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 0
Crossing | Bldg C | 2605-C12 | x | 35 | 13 | 455 | 32 | 1 | 2 | 455 | 0 | 32 | 2 | 0 | 96 | 35 | 0 | 0 | 0 | 0 | 96 | 1 | 1 | 7 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0
Crossing | Bldg D | 2606-D01 | x | 34 | 11 | 374 | 31 | 2 | 1 | 374 | 0 | 33 | 2 | 0 | 90 | 35 | 0 | 0 | 0 | 0 | 90 | 1 | 0 | 9 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0
Crossing | Bldg D | 2606-D02 | x | 34 | 11 | 374 | 6 | 4 | 2 | 374 | 0 | 23 | 5 | 1 | 82 | 0 | 30 | 7 | 30 | 30 | 112 | 1 | 1 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 0
Crossing | Bldg D | 2606-D03 | x | 34 | 11 | 374 | 6 | 4 | 2 | 374 | 0 | 23 | 5 | 1 | 82 | 0 | 30 | 7 | 30 | 30 | 112 | 1 | 1 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 0
Crossing | Bldg D | 2606-D04 | x | 34 | 11 | 374 | 31 | 2 | 1 | 374 | 0 | 33 | 2 | 0 | 90 | 35 | 0 | 0 | 0 | 0 | 90 | 1 | 0 | 9 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0
Crossing | Bldg D | 2606-D05 | x | 34 | 11 | 374 | 31 | 2 | 1 | 374 | 0 | 33 | 2 | 0 | 90 | 35 | 0 | 0 | 0 | 0 | 90 | 1 | 0 | 9 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0
Crossing | Bldg D | 2606-D06 | x | 30 | 11 | 330 | 30 | 5 | 2 | 330 | 0 | 31 | 5 | 1 | 82 | 0 | 30 | 7 | 30 | 30 | 112 | 1 | 1 | 15 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 0
Crossing | Bldg D | 2606-D07 | x | 30 | 11 | 330 | 30 | 5 | 2 | 330 | 0 | 31 | 5 | 1 | 82 | 0 | 30 | 7 | 30 | 30 | 112 | 1 | 1 | 15 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 0
Crossing | Bldg D | 2606-D08 | x | 34 | 11 | 374 | 31 | 2 | 1 | 374 | 0 | 33 | 2 | 0 | 90 | 35 | 0 | 0 | 0 | 0 | 90 | 1 | 0 | 9 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0
Crossing | Bldg D | 2606-D09 | x | 34 | 11 | 374 | 31 | 2 | 1 | 374 | 0 | 33 | 2 | 0 | 90 | 35 | 0 | 0 | 0 | 0 | 90 | 1 | 0 | 9 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0
Crossing | Bldg D | 2606-D10 | x | 34 | 11 | 374 | 6 | 5 | 2 | 374 | 0 | 23 | 5 | 1 | 82 | 0 | 30 | 7 | 30 | 30 | 112 | 1 | 1 | 15 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 0
Crossing | Bldg D | 2606-D11 | x | 34 | 11 | 374 | 6 | 5 | 2 | 374 | 0 | 23 | 5 | 1 | 82 | 0 | 30 | 7 | 30 | 30 | 112 | 1 | 1 | 15 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 0
Crossing | Bldg D | 2606-D12 | x | 34 | 11 | 374 | 31 | 2 | 1 | 374 | 0 | 33 | 2 | 0 | 90 | 35 | 0 | 0 | 0 | 0 | 90 | 1 | 0 | 9 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0
Crossing | Bldg E | 2607-E01 | x | 35 | 11 | 385 | 3 | 4 | 1 | 385 | 0 | 24 | 4 | 1 | 92 | 11 | 28 | 7 | 16 | 16 | 120 | 1 | 1 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0
Crossing | Bldg E | 2607-E05 | x | 35 | 11 | 385 | 3 | 4 | 1 | 385 | 0 | 24 | 4 | 1 | 92 | 0 | 28 | 7 | 30 | 30 | 120 | 1 | 0 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0
Crossing | Bldg E | 2607-E06 | x | 30 | 11 | 330 | 6 | 5 | 2 | 330 | 0 | 27 | 5 | 1 | 82 | 11 | 28 | 7 | 16 | 16 | 110 | 1 | 1 | 17 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 0
Crossing | Bldg E | 2607-E10 | x | 35 | 11 | 385 | 3 | 4 | 1 | 385 | 0 | 24 | 4 | 1 | 92 | 0 | 28 | 7 | 30 | 30 | 120 | 1 | 0 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0
Crossing | Bldg E | 2607-E11 | x | 30 | 11 | 330 | 6 | 5 | 2 | 330 | 0 | 27 | 5 | 1 | 82 | 11 | 37 | 8 | 16 | 16 | 119 | 1 | 1 | 17 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 0
Crossing | Bldg E | 2607-E15 | x | 35 | 11 | 385 | 3 | 4 | 1 | 385 | 0 | 24 | 4 | 1 | 92 | 0 | 28 | 7 | 30 | 30 | 120 | 1 | 0 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0
Crossing | Bldg E | 2607-E02 | x | 35 | 13 | 455 | 38 | 1 | 1 | 455 | 0 | 31 | 2 | 0 | 96 | 14 | 0 | 0 | 35 | 35 | 96 | 1 | 0 | 9 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0
Crossing | Bldg E | 2607-E04 | x | 35 | 13 | 455 | 38 | 2 | 1 | 455 | 0 | 31 | 2 | 0 | 96 | 13 | 0 | 0 | 35 | 35 | 96 | 1 | 1 | 9 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0
Crossing | Bldg E | 2607-E07 | x | 35 | 13 | 455 | 38 | 2 | 1 | 455 | 0 | 31 | 2 | 0 | 96 | 14 | 0 | 0 | 35 | 35 | 96 | 1 | 0 | 9 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0
Crossing | Bldg E | 2607-E09 | x | 35 | 13 | 455 | 38 | 2 | 1 | 455 | 0 | 31 | 2 | 0 | 96 | 13 | 0 | 0 | 35 | 35 | 96 | 1 | 1 | 9 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0
Crossing | Bldg E | 2607-E12 | x | 35 | 13 | 455 | 38 | 2 | 1 | 455 | 0 | 31 | 2 | 0 | 96 | 14 | 0 | 0 | 35 | 35 | 96 | 1 | 0 | 9 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0
Crossing | Bldg E | 2607-E14 | x | 35 | 13 | 455 | 38 | 2 | 1 | 455 | 0 | 31 | 2 | 0 | 96 | 13 | 0 | 0 | 35 | 35 | 96 | 1 | 1 | 9 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0
Crossing | Bldg E Studio | 2607-E03 | x | 35 | 15 | 552 | 29 | 4 | 1 | 552 | 0 | 36 | 6 | 1 | 100 | 15 | 37 | 9 | 70 | 70 | 137 | 1 | 1 | 94 | 6 | 0 | 0 | 0 | 0 | 0 | 2 | 0
Crossing | Bldg E Studio | 2607-E08 | x | 35 | 15 | 552 | 29 | 4 | 1 | 552 | 0 | 36 | 6 | 1 | 100 | 15 | 37 | 9 | 70 | 70 | 137 | 1 | 1 | 94 | 6 | 0 | 0 | 0 | 0 | 0 | 2 | 0
Crossing | Bldg E Studio | 2607-E13 | x | 35 | 15 | 552 | 29 | 4 | 1 | 552 | 0 | 36 | 6 | 1 | 100 | 15 | 37 | 9 | 70 | 70 | 137 | 1 | 1 | 94 | 6 | 0 | 0 | 0 | 0 | 0 | 2 | 0

## Task Template Data
TASK TEMPLATES
Station | Department ID | Task # | Name | Task Description | Prerequisite task | Min Workers | Max Workers | Module attributes | Ranked skills
1 | Structure | 1 | Layout Floor System | Layout Floor System, Attach Joist, Install Foam Blocks/ 5/8"Drywall |  | 2 | 2 | 1 | A,H,P,O
1 | Structure | 2 | Floor System Completion | Deck the Floor (Screw), Cut Access Panels, Snap Wall Lines, | 2 | 2 | 6 | 1 | A,H,P,O
2 | MEP | 3 | Underfloor Plumbing | Layout Plumbing Fixtures, Drill Holes, Stub Down Pipes, Assemble DWV/Test, Assemble Water/Test |  | 1 | 3 | 10 | C,K
2 | MEP | 4 | Underfloor Electrical | Layout Electrical Fixtures, Drill Homes, Pull Wire, Install Quick Connects |  | 1 | 3 | 9 | B,J
2 | MEP | 5 | Underfloor HVAC | Layout Line Sets, Condensate Lines, Secure Lines |  | 1 | 2 | 19 | D
3 | Structure | 6 | Wall Building | Layout Drywall, Assemble Wall Sections, Square Walls, Secure to Drywall, Cut off Excess Drywall, Store in Rack |  | 2 | 6 | 18 | A,H,P,O
3 | Structure | 7 | Fire Tape Fire Walls | Fire Tape Fire Walls Prior to Wall Set | 6 | 1 | 2 | 13+16 | F,E,P
4 | Structure | 8 | Install Walls on Floor | Install 3 Exterior Walls, Interior Walls, Stairs, Place Tubs, Lag Walls together, Install Rockwool Fire Separation |  | 2 | 6 | 18 | A,H,P,O
6 | MEP | 8 | Complete Rough Plumbing | Complete In wall Plumbing, Install Plumbing Nail Plates |  | 1 | 3 | 10 | C,K
6 | MEP | 9 | Electrical Wall J-boxes | Cut Out / Install Boxes |  | 1 | 4 | 9 | B,J
| Building Envelope | 10 | Ceiling Construction |  |  |  |  | 3
7 | Building Envelope | 11 | Roof Construction | Layout Drywall, Build Ceiling / Roof, Attach Drywall, Fire Drywall Blocks Installed, Foam Blocks Installed, Set Roof on Box |  | 2 | 6 | 23 | A,H,P,O
8 | MEP | 12 | HVAC Rough In | Layout HVAC, Install Risers, Install Ducting, Install line sets in walls, Insure any required blocking is installed, Cut Register Holes |  | 1 | 4 | 21 | D
8 | MEP | 13 | Complete Electrical Rough | Pull Wires, Strip wires in boxes, Panel Build Out, Smerf Tues, Conduit To Panel, Risers to 2nd Floor |  | 1 | 4 | 9 | B,J
9 | Building Envelope | 14 | Mud Ceiling / Roof in Rack | 1st Coat of Mud on Ceiling |  | 1 | 2 | 3 | F,E
10 | MEP | 15 | Rough Plumbing Completion | Top out Plumbing, Test DWV, Test Water |  | 1 | 4 | 10 | C,K
10 | MEP | 16 | Rough Mechanical Completion | Dryer Vent Exit, Fart Fans Exit, Furnace Exhaust, Furnace Intake, Riser Extensions To 2nd Floor Register Location in Ceiling |  | 1 | 4 | 21 | D
10 | Building Envelope | 17 | Rough Framing Complete | Complete Any Rough Framing, Soffits Built for MEP | 16 | 1 | 3 | 20,21 | A,H,P,O
11 | Building Envelope | 18 | Foam all Penetrations | Foam All Penetrations, Fire Foam and Fire Penetrations, NOTHING on Fire Sprinklers |  | 1 | 2 | 9 | P
11 | Building Envelope | 19 | Insulation Install | Wall Batt insulation, Interior Sound/Fire Wall Insulation, Blown-In Insulation, Blown in Vent Baffles Installed, Ceiling Joist Batt Blocks | 18 | 1 | 4 | 13+17 | P
11 | Building Envelope | 20 | Back Panel | Complete Drywall Back Panel |  | 1 | 5 | 18 | E,F,A,P
12 | Building Envelope | 21 | Exterior OSB / Window Nailers | Complete Exterior OSB, Install Window and Door 3/4" OSB Nailers |  | 2 | 8 | 3 | A,H,P,O
12 | Building Envelope | 22 | Roof OSB Decking | Complete Roof 5/8" OSB |  | 2 | 6 | 23 | A,H,P,O
12 | Building Envelope | 23 | Exterior Fire Wall Drywall | Complete Exterior Fire Wall Drywall | 21 | 2 | 4 | 13 | E,F,A,P
| Building Envelope | 24 | Fire Tape Fire Walls |  | 23 |  |  | 13
12 | Building Envelope | 25 | Interior Tape / Mud 1st Coat | Interior Tape / Mud 1st Coat |  | 2 | 6 | 18 | F
12 | Building Envelope | 26 | Dry Time First Coat | Dry Time First Coat | 25 | 0 | 0
12 | Building Envelope | 27 | Interior Tape / Mud 2nd Coat | Interior Tape / Mud 2nd Coat | 26 | 2 | 6 | 18 | F
12 | Building Envelope | 28 | Dry Time 2nd Coat | Dry Time 2nd Coat | 27 | 0 | 0
13 | Building Envelope | 29 | Exterior Foam Board Insulation | Complete Exterior R-Max |  | 2 | 6 | 12+13 | A,H,P,O
13 | Building Envelope | 30 | Final Sand of Drywall / Texture Prep | Final Sand of Drywall, Tape All Opening |  | 2 | 6 | 18 | F
13 | Interior / Exterior | 31 | Texture | Prep Machine / Materials, Spray Texture, Clean up | 30 | 2 | 4 | 18 | G
13 | Interior / Exterior | 32 | Dry Time Texture | Dry Time | 31 | 2 | 2
13 | Interior / Exterior | 33 | Paint - Wall Primer | Spray Flat Paint | 32 | 1 | 1 | 18 | I
13 | Interior / Exterior | 34 | Paint - Spray Semi-Gloss Paint | Spray Semi-Gloss Paint | 33 | 1 | 1 |  | I
14 | Interior / Exterior | 35 | Install Windows / Patio Doors | Install windows, Patio Doors, Caulk Window and Door Flanges, Tape Windows/Doors, Foam Inside of Windows Doors |  | 2 | 6 | 6 | H
14 | Interior / Exterior | 36 | Cabinet Install | Kitchen and Bath Cabinets Install |  | 2 | 6 | 4 | H
14 | MEP Finish | 37 | Electrical Final Trim Out | Receptacles Installed, Switched Installed, Lights Installed, Breakers Installed |  | 1 | 3 | 9 | J
14 | MEP Finish | 38 | Electrical Functionality Testing | Complete Functionality Test | 38 | 1 | 1 | 9 | J
15 | Interior / Exterior | 39 | Siding Install | Install - Install Siding |  | 2 | 6 | 27 | H,A,P
15 | Interior / Exterior | 40 | Fascia / Soffit Install | Install Fascia / Soffit | 39 | 2 | 6
15 | Interior / Exterior | 41 | Flooring Install | Install Flooring (no carpet) |  | 1 | 3 | 7 | H,A,P
16 | Interior / Exterior | 42 | Door Installation | Interior and Exterior Door Install, Casing Installed |  | 2 | 6 | 5 | H,A,P
16 | Interior / Exterior | 43 | Window Jambs/Casings & Baseboard Installed | Window Jambs/Casing Installed, Patio Door Jambs/Casing Installed, Baseboard Installed |  | 2 | 6 | 6,5,18 | H,A,P
16 | Interior / Exterior | 44 | Paint Prep For BaseBoard and Trim | Prep For Paint of Baseboard / Trim, Mask Doors, Window Glass | 42,43 | 1 | 4 | 18 | I,P
16 | Interior / Exterior | 45 | Paint Prep Exterior | Caulking Siding, Tape of Windows and Doors |  | 1 | 4 | 27 | I,P
17 | Interior / Exterior | 46 | Exterior Paint | Paint Exterior including Doors |  | 1 | 1 | 27 | I,G
17 | Interior / Exterior | 47 | Interior Trim Paint | Interior Paint, Door Jambs / Casing, Baseboards, Window Jambs, Casings |  | 1 | 1 | 5,6 | I,G
18 | Interior / Exterior | 48 | Install Door Handle/Lock Hardware | Install hardware on Interior Doors, Exterior Doors, Towel Bars, Toilet Paper Holder |  | 1 | 3 | 5 | H,P
18 | Interior / Exterior | 49 | Install Roofing | Drip Edge, Underlayment, and Finally. Roofing |  | 1 | 4 | 25 | L
18 | MEP Finish | 50 | Install Final Plumbing Trims | Plumbing Trims, Faucets, Under Sink Makeup |  | 1 | 3 | 10 | K
19 | Final Close-Out / Wrap | 51 | Exterior Shrink Wrap | Ceiling Wrap Spacer, Wrapping Installed |  | 2 | 4 | 1 | P
19 | Interior / Exterior | 52 | Install Carpet | Install Carpet, Plastic Carpet |  | 2 | 2 | 8 | M
19 | Final Close-Out / Wrap | 53 | Load and Install Appliances | Load Appliances, Install Appliances |  | 1 | 4 | 4 | P
19 | Final Close-Out / Wrap | 54 | Load Shiploose | Load Shiploose List |  | 1 | 4 | 3 | P
20 | MEP Finish | 55 | Complete Remaining Underfloor Plumbing | Complete any P-Traps |  | 1 | 4 | 10 | C
20 | MEP Finish | 56 | Final Plumbing Fixture Testing | Fixture Test on Plumbing | 55 | 1 | 2 | 10 | C
20 | Final Close-Out / Wrap | 57 | Remove Skates - Build Attachment Points | Remove Skates, Install missing Drywall, OSB, Foam Board, Final Plumbing Foaming |  | 1 | 4 | 1 | P
20 | Final Close-Out / Wrap | 58 | Final Clean | Final Clean |  | 1 | 4 | 1 | P
21 | Final Close-Out / Wrap | 59 | Move Box Outside | Move Box to Outside Storage |  | 2 | 3 | 3 | P
Pre Assembly | Preassembly | 60 | Floor System Pre Cut Package | Cut Joist, Cut OSB, Put in Package, Cut LVL to Length |  | 2 | 2 | 1 | O,A
Pre Assembly | Preassembly | 61 | Wall Building Kits | Cut Walls for Box, Put Package Together, Organize and Label |  | 1 | 1 | 18 | O,A
Pre Assembly | Preassembly | 62 | Measure walls for Drywall cut | Measure all left to right dimensions, Label on floor plan drawing, number walls |  | 1 | 1 | 18 | O,A
Pre Assembly | Preassembly | 63 | Ceiling/ Roof System Pre Cut Package | Cut Ceiling Joist, Cut LVL's to length, cut any blocks |  | 1 | 1 | 3 | O,A
Pre Assembly | Preassembly | 64 | Ceiling Roof System Cut and Package Drywall | Cut and prepare drywall pile to put on material bridge with correct layout order |  | 2 | 2 | 3 | O,A
Pre Assembly | Preassembly | 65 | Back Panel Drywall Cut | Cut and label size and wall number that match measure floor plan drawing notes, put on cart and deliver |  | 2 | 2 | 18 | O,A
Pre Assembly | Preassembly | 66 | Insulation Prep | Cut Batts to length, Cut 2" Foam Blocks, Cut Floor Rim Joist Blocks, Cut Ceiling Joist Batt Blocks |  | 1 | 1 | 12+13 | O,P
Pre Assembly | Preassembly | 67 | Cut Window and Door Nailers | Cut 2" Strips of OSB for exterior window and door nailers |  | 1 | 1 | 5+6 | O,P
Pre Assembly | Preassembly | 68 | Window Jambs & Casings | Build One Piece Window Jamb Boxes with Casing for all Windows |  | 2 | 2 | 6 | H,O
Pre Assembly | Preassembly | 69 | Pre Made Door Casings | Build Pre Made Door Casings for Each Door, Casings Kits for Patio Doors |  |  |  | 5 | H,O
Pre Assembly | Preassembly | 70 | Prep - Paint Interior / Exterior Doors | Paint Interior Door Slabs |  | 2 | 2 | 5 | I
Pre Assembly | Preassembly | 71 | Prep Bathroom Sinks | Install Faucets in Bathroom Vanity Sinks |  | 1 | 1 | 28 | K,O,P
Pre Assembly | Preassembly | 72 | Ceiling Pre-Warp Spacers Cut | Cut Siding Strip Correct Length for Ceiling Wrap, Cut Spacer Blocks |  | 1 | 1 | 1 | O,A
Pre Assembly | Preassembly | 73 | Cut Shipping OSB for Windows / Doors | Cut OSB for End Windows / Doors for Shipping, Cut 2x4 for OSB to mount to |  | 1 | 1 | 6 | O,A

## TIme Study Data
TIME STUDIES
Task # | Task Template Name | Module Attributes | Value | Clock Time | Laborers
1 | Layout Floor System | 1 | 62.5 | 1.5 | 4 | 6
2 | Floor System Completion | 1 | 62.5 | 4 | 4 | 16
3 | Underfloor Plumbing | 10 | 8 | 5 | 2 | 10
4 | Underfloor Electrical | 9 | 27 | 6 | 1 | 6
5 | Underfloor HVAC | 19 | 4 | 5 | 1 | 5
6 | Wall Building | 18 | 61 | 5.5 | 4 | 22
7 | Fire Tape Fire Walls | 13+16 | 61 | 1 | 6 | 6
8 | Install Walls on Floor | 18 | 221 | 8.5 | 3 | 25.5
8 | Complete Rough Plumbing | 10 | 5 | 10.8 | 2 | 21.6
9 | Electrical Wall J-boxes | 9 | 44 | 15 | 2 | 30
10 | Ceiling Construction | 3 | 45.5 | 3.5 | 4 | 14
11 | Roof Construction | 23 | 45.6 | 8 | 4 | 32
12 | HVAC Rough In | 21 | 37 | 6 | 1 | 6
13 | Complete Electrical Rough | 9 | 44 | 8 | 2 | 16
14 | Mud Ceiling / Roof in Rack | 3 | 720 | 2 | 2 | 4
15 | Rough Plumbing Completion | 10 | 7 | 8 | 2 | 16
16 | Rough Mechanical Completion | 21 | 105 | 8 | 3 | 24
17 | Rough Framing Complete | 20,21 | 30 | 2 | 3 | 6
18 | Foam all Penetrations | 9 | 44 | 2 | 1 | 2
19 | Insulation Install | 13+17 | 128 | 1.7 | 3 | 5.1
20 | Back Panel | 18 | 130 | 7 | 2 | 14
21 | Exterior OSB / Window Nailers | 3 | 700 | 10 | 2 | 20
22 | Roof OSB Decking | 23 | 730 | 6.5 | 4 | 26
23 | Exterior Fire Wall Drywall | 13 | 49 | 5 | 2 | 10
24 | Fire Tape Exterior Fire Wall | 13 | 49 | 2 | 2 | 4
25 | Interior Tape / Mud 1st Coat | 18 | 130 | 5.5 | 6 | 33
26 | Dry Time First Coat |  |  | 2 |  | 0
27 | Interior Tape / Mud 2nd Coat | 18 | 130 | 5 | 6 | 30
28 | Dry Time 2nd Coat |  |  | 2 |  | 0
29 | Exterior Foam Board Insulation | 12+13 | 35, 50 | 5.25 | 2 | 10.5
30 | Final Sand of Drywall / Texture Prep | 18 | 130 | 2 | 2 | 4
31 | Texture | 18 | 220 | 2 | 2 | 4
32 | Dry Time Texture |  |  | 3 |  | 0
33 | Paint - Wall Primer | 18 | 220 | 1.5 | 1 | 1.5
34 | Paint - Spray Semi-Gloss Paint |  | 220 | 1.5 | 1 | 1.5
35 | Install Windows / Patio Doors | 6 | 5 | 2 | 3 | 6
36 | Cabinet Install | 4 | 41 | 9.5 | 2 | 19
37 | Electrical Final Trim Out | 9 | 14 | 2 | 1 | 2
38 | Electrical Functionality Testing | 9 | 14 | 1 | 1 | 1
39 | Siding Install | 27 |  | 3.3 | 4 | 13.2
40 | Fascia / Soffit Install | 26 | 77 | 3.5 | 5 | 17.5
41 | Flooring Install | 7 |  | 8.5 | 1 | 8.5
42 | Door Installation | 5 | 4 | 3 | 1 | 3
43 | Window Jambs/Casings & Baseboard Installed | 6,5,18 | 4, 2, 0123 | 3 | 2 | 6
44 | Paint Prep For BaseBoard and Trim | 18 | 130 | 1.5 | 1 | 1.5
45 | Paint Prep Exterior | 27 | 693 | 8 | 3 | 24
46 | Exterior Paint | 27 | 693 | 2.5 | 1 | 2.5
47 | Interior Trim Paint | 5,6 | 2026-04-02 | 5.5 | 2 | 11
48 | Install Door Handle/Lock Hardware | 5 | 2 | 1.5 | 2 | 3
49 | Install Roofing | 25 | 700 | 6 | 6 | 36
50 | Install Final Plumbing Trims | 10 | 8 | 2 | 2 | 4
51 | Exterior Shrink Wrap | 1 | 65 | 5 | 2 | 10
52 | Install Carpet | 8 | 100 | 3 | 2 | 6
53 | Load and Install Appliances | 4 | 41 | 1.5 | 1 | 1.5
54 | Load Shiploose | 3 | 693 | 1.5 | 2 | 3
55 | Complete Remaining Underfloor Plumbing | 10 | 6 | 3 | 1 | 3
56 | Final Plumbing Fixture Testing | 10 | 6 | 3 | 1 | 3
57 | Remove Skates - Build Attachment Points | 1 | 65 | 4 | 2 | 8
58 | Final Clean | 1 | 49 | 2 | 3 | 6
59 | Move Box Outside | 3 | 800 | 2 | 1 | 2
60 | Floor System Pre Cut Package | 1 |  |  |  | 0
61 | Wall Building Kits | 18 |  |  |  | 0
62 | Measure walls for Drywall cut | 18 |  |  |  | 0
63 | Ceiling/ Roof System Pre Cut Package | 3 |  |  |  | 0
64 | Ceiling Roof System Cut and Package Drywall | 3 |  |  |  | 0
65 | Back Panel Drywall Cut | 18 |  |  |  | 0
66 | Insulation Prep | 12+13 |  |  |  | 0
67 | Cut Window and Door Nailers | 5+6 |  |  |  | 0
68 | Window Jambs & Casings | 6 |  |  |  | 0
69 | Pre Made Door Casings | 5 |  |  |  | 0
70 | Prep - Paint Interior / Exterior Doors | 5 |  |  |  | 0
71 | Prep Bathroom Sinks | 28 |  |  |  | 0
72 | Ceiling Pre-Warp Spacers Cut | 1 |  |  |  | 0
73 | Cut Shipping OSB for Windows / Doors | 6 |  |  |  | 0