## Verification Report
Planning Validation Report
Status | ✅ PASS
Timestamp | 2026-01-10T02:12:45.920Z
Stats
Total Assignments | 67
Valid Assignments | 67
Invalid Assignments | 0
Constraint Checks | Status | Violations
Hard: Min Workers | PASS | 0
Hard: Max Workers | PASS | 0
Hard: Dependencies | PASS | 0
Hard: Double Booking | PASS | 0

## Assignments
Task | TaskId | Worker | Start | End
Baffels and Blown In Insulation | t_3 | w_17 | 2024-01-01T14:30:00.000Z | 2024-01-01T17:00:00.000Z
Baffels and Blown In Insulation | t_3 | w_18 | 2024-01-01T14:30:00.000Z | 2024-01-01T17:00:00.000Z
Complete Drywall Back Panel | t_5 | w_10 | 2024-01-01T11:00:00.000Z | 2024-01-01T14:30:00.000Z
Complete Drywall Back Panel | t_5 | w_9 | 2024-01-01T11:00:00.000Z | 2024-01-01T15:00:00.000Z
Complete Drywall Back Panel | t_5 | w_12 | 2024-01-01T11:30:00.000Z | 2024-01-01T14:30:00.000Z
Complete Drywall Back Panel | t_5 | w_3 | 2024-01-01T11:30:00.000Z | 2024-01-01T12:00:00.000Z
Complete Drywall Back Panel | t_5 | w_13 | 2024-01-01T12:00:00.000Z | 2024-01-01T14:30:00.000Z
Complete Exterior Fire Wall | t_8 | w_11 | 2024-01-01T07:00:00.000Z | 2024-01-01T09:30:00.000Z
Complete Exterior Fire Wall | t_8 | w_17 | 2024-01-01T07:00:00.000Z | 2024-01-01T09:30:00.000Z
Complete Exterior Fire Wall | t_8 | w_18 | 2024-01-01T07:00:00.000Z | 2024-01-01T09:30:00.000Z
Complete Exterior Fire Wall | t_8 | w_19 | 2024-01-01T07:00:00.000Z | 2024-01-01T09:30:00.000Z
Complete Exterior OSB | t_6 | w_11 | 2024-01-01T09:30:00.000Z | 2024-01-01T14:30:00.000Z
Complete Exterior OSB | t_6 | w_17 | 2024-01-01T09:30:00.000Z | 2024-01-01T14:30:00.000Z
Complete Exterior OSB | t_6 | w_18 | 2024-01-01T09:30:00.000Z | 2024-01-01T14:30:00.000Z
Complete Exterior OSB | t_6 | w_19 | 2024-01-01T09:30:00.000Z | 2024-01-01T14:30:00.000Z
Complete Exterior R-Max | t_11 | w_22 | 2024-01-01T13:30:00.000Z | 2024-01-01T17:00:00.000Z
Complete Exterior R-Max | t_11 | w_23 | 2024-01-01T13:30:00.000Z | 2024-01-01T17:00:00.000Z
Complete Exterior R-Max | t_11 | w_24 | 2024-01-01T13:30:00.000Z | 2024-01-01T17:00:00.000Z
Complete Roof 5/8" OSB | t_7 | w_13 | 2024-01-01T11:30:00.000Z | 2024-01-01T12:00:00.000Z
Complete Roof 5/8" OSB | t_7 | w_4 | 2024-01-01T11:30:00.000Z | 2024-01-01T12:00:00.000Z
Complete Roof 5/8" OSB | t_7 | w_20 | 2024-01-01T13:30:00.000Z | 2024-01-01T16:30:00.000Z
Complete Roof 5/8" OSB | t_7 | w_21 | 2024-01-01T13:30:00.000Z | 2024-01-01T16:30:00.000Z
Complete Roof 5/8" OSB | t_7 | w_6 | 2024-01-01T13:30:00.000Z | 2024-01-01T16:30:00.000Z
Complete Roof 5/8" OSB | t_7 | w_7 | 2024-01-01T13:30:00.000Z | 2024-01-01T16:30:00.000Z
Fascia Soffit | t_18 | w_1 | 2024-01-01T12:00:00.000Z | 2024-01-01T16:30:00.000Z
Fascia Soffit | t_18 | w_2 | 2024-01-01T12:00:00.000Z | 2024-01-01T16:30:00.000Z
Fascia Soffit | t_18 | w_3 | 2024-01-01T12:00:00.000Z | 2024-01-01T16:30:00.000Z
Fascia Soffit | t_18 | w_4 | 2024-01-01T12:00:00.000Z | 2024-01-01T16:00:00.000Z
Final sand of drywall | t_12 | w_20 | 2024-01-01T07:00:00.000Z | 2024-01-01T09:00:00.000Z
Flooring Install | t_20 | w_11 | 2024-01-01T16:30:00.000Z | 2024-01-01T17:00:00.000Z
Flooring Install | t_20 | w_4 | 2024-01-01T16:30:00.000Z | 2024-01-01T17:00:00.000Z
Flooring Install | t_20 | w_8 | 2024-01-01T16:30:00.000Z | 2024-01-01T17:00:00.000Z
Flooring Install | t_20 | w_9 | 2024-01-01T16:30:00.000Z | 2024-01-01T17:00:00.000Z
Install electrical trim | t_17 | w_5 | 2024-01-01T14:00:00.000Z | 2024-01-01T17:00:00.000Z
Install electrical trim | t_17 | w_10 | 2024-01-01T14:30:00.000Z | 2024-01-01T17:00:00.000Z
Install electrical trim | t_17 | w_11 | 2024-01-01T14:30:00.000Z | 2024-01-01T16:00:00.000Z
Install Siding | t_19 | w_21 | 2024-01-01T07:00:00.000Z | 2024-01-01T13:30:00.000Z
Install Siding | t_19 | w_22 | 2024-01-01T07:00:00.000Z | 2024-01-01T13:30:00.000Z
Install Siding | t_19 | w_23 | 2024-01-01T07:00:00.000Z | 2024-01-01T13:30:00.000Z
Install Siding | t_19 | w_24 | 2024-01-01T07:00:00.000Z | 2024-01-01T13:30:00.000Z
Install Siding | t_19 | w_7 | 2024-01-01T08:30:00.000Z | 2024-01-01T13:30:00.000Z
Install Siding | t_19 | w_20 | 2024-01-01T09:00:00.000Z | 2024-01-01T13:30:00.000Z
Install Siding | t_19 | w_5 | 2024-01-01T09:30:00.000Z | 2024-01-01T14:00:00.000Z
Install Siding | t_19 | w_6 | 2024-01-01T09:30:00.000Z | 2024-01-01T13:30:00.000Z
Interior Tape / Mud 1st Coat | t_9 | w_10 | 2024-01-01T07:00:00.000Z | 2024-01-01T11:00:00.000Z
Interior Tape / Mud 1st Coat | t_9 | w_12 | 2024-01-01T07:00:00.000Z | 2024-01-01T11:30:00.000Z
Interior Tape / Mud 1st Coat | t_9 | w_13 | 2024-01-01T07:00:00.000Z | 2024-01-01T11:30:00.000Z
Interior Tape / Mud 1st Coat | t_9 | w_14 | 2024-01-01T07:00:00.000Z | 2024-01-01T11:00:00.000Z
Interior Tape / Mud 1st Coat | t_9 | w_15 | 2024-01-01T07:00:00.000Z | 2024-01-01T11:00:00.000Z
Interior Tape / Mud 1st Coat | t_9 | w_16 | 2024-01-01T07:00:00.000Z | 2024-01-01T11:00:00.000Z
Interior Tape / Mud 1st Coat | t_9 | w_8 | 2024-01-01T07:00:00.000Z | 2024-01-01T11:00:00.000Z
Interior Tape / Mud 1st Coat | t_9 | w_9 | 2024-01-01T07:00:00.000Z | 2024-01-01T11:00:00.000Z
Interior Tape / Mud 2nd Coat | t_10 | w_14 | 2024-01-01T11:00:00.000Z | 2024-01-01T15:00:00.000Z
Interior Tape / Mud 2nd Coat | t_10 | w_15 | 2024-01-01T11:00:00.000Z | 2024-01-01T15:00:00.000Z
Interior Tape / Mud 2nd Coat | t_10 | w_16 | 2024-01-01T11:00:00.000Z | 2024-01-01T15:00:00.000Z
Interior Tape / Mud 2nd Coat | t_10 | w_8 | 2024-01-01T11:00:00.000Z | 2024-01-01T15:00:00.000Z
Kitchen and Bath Cabinets Install | t_16 | w_1 | 2024-01-01T07:00:00.000Z | 2024-01-01T12:00:00.000Z
Kitchen and Bath Cabinets Install | t_16 | w_2 | 2024-01-01T07:00:00.000Z | 2024-01-01T12:00:00.000Z
Kitchen and Bath Cabinets Install | t_16 | w_3 | 2024-01-01T07:00:00.000Z | 2024-01-01T11:30:00.000Z
Kitchen and Bath Cabinets Install | t_16 | w_4 | 2024-01-01T07:00:00.000Z | 2024-01-01T11:30:00.000Z
Spray paint | t_14 | w_8 | 2024-01-01T15:00:00.000Z | 2024-01-01T16:00:00.000Z
Spray Texture | t_13 | w_7 | 2024-01-01T07:00:00.000Z | 2024-01-01T08:30:00.000Z
Tape and install windows | t_15 | w_12 | 2024-01-01T14:30:00.000Z | 2024-01-01T16:45:00.000Z
Tape and install windows | t_15 | w_13 | 2024-01-01T14:30:00.000Z | 2024-01-01T15:00:00.000Z
Tape and install windows | t_15 | w_19 | 2024-01-01T14:30:00.000Z | 2024-01-01T17:00:00.000Z
Wall Batt insulation | t_2 | w_5 | 2024-01-01T07:00:00.000Z | 2024-01-01T09:30:00.000Z
Wall Batt insulation | t_2 | w_6 | 2024-01-01T07:00:00.000Z | 2024-01-01T09:30:00.000Z

## Completion Status
Task | TaskId | DoneHours | TotalHours | Progress | Status
Wall Batt insulation | t_2 | 5.00 | 5.00 | 100% | ✅ Complete
Baffels and Blown In Insulation | t_3 | 5.00 | 5.50 | 91% | 🚧 In Progress
Ceiling Rim Insulation | t_4 | 0.00 | 4.00 | 0% | 🛑 Not Started
Complete Drywall Back Panel | t_5 | 13.50 | 13.50 | 100% | ✅ Complete
Complete Exterior OSB | t_6 | 20.00 | 20.00 | 100% | ✅ Complete
Complete Roof 5/8" OSB | t_7 | 13.00 | 13.00 | 100% | ✅ Complete
Complete Exterior Fire Wall | t_8 | 10.00 | 10.00 | 100% | ✅ Complete
Interior Tape / Mud 1st Coat | t_9 | 33.00 | 33.00 | 100% | ✅ Complete
Interior Tape / Mud 2nd Coat | t_10 | 16.00 | 16.00 | 100% | ✅ Complete
Complete Exterior R-Max | t_11 | 10.50 | 10.50 | 100% | ✅ Complete
Final sand of drywall | t_12 | 2.00 | 2.00 | 100% | ✅ Complete
Spray Texture | t_13 | 1.50 | 1.50 | 100% | ✅ Complete
Spray paint | t_14 | 1.00 | 1.00 | 100% | ✅ Complete
Tape and install windows | t_15 | 5.25 | 5.25 | 100% | ✅ Complete
Kitchen and Bath Cabinets Install | t_16 | 19.00 | 19.00 | 100% | ✅ Complete
Install electrical trim | t_17 | 7.00 | 7.00 | 100% | ✅ Complete
Fascia Soffit | t_18 | 17.50 | 17.50 | 100% | ✅ Complete
Install Siding | t_19 | 44.00 | 44.00 | 100% | ✅ Complete
Flooring Install | t_20 | 2.00 | 9.00 | 22% | 🚧 In Progress

## Idle Workers
Worker | Start | End
w_13 | 2024-01-01T15:00:00.000Z | 2024-01-01T17:00:00.000Z
w_14 | 2024-01-01T15:00:00.000Z | 2024-01-01T17:00:00.000Z
w_15 | 2024-01-01T15:00:00.000Z | 2024-01-01T17:00:00.000Z
w_16 | 2024-01-01T15:00:00.000Z | 2024-01-01T17:00:00.000Z
w_9 | 2024-01-01T15:00:00.000Z | 2024-01-01T16:30:00.000Z
w_11 | 2024-01-01T16:00:00.000Z | 2024-01-01T16:30:00.000Z
w_4 | 2024-01-01T16:00:00.000Z | 2024-01-01T16:30:00.000Z
w_8 | 2024-01-01T16:00:00.000Z | 2024-01-01T16:30:00.000Z
w_1 | 2024-01-01T16:30:00.000Z | 2024-01-01T17:00:00.000Z
w_2 | 2024-01-01T16:30:00.000Z | 2024-01-01T17:00:00.000Z
w_20 | 2024-01-01T16:30:00.000Z | 2024-01-01T17:00:00.000Z
w_21 | 2024-01-01T16:30:00.000Z | 2024-01-01T17:00:00.000Z
w_3 | 2024-01-01T16:30:00.000Z | 2024-01-01T17:00:00.000Z
w_6 | 2024-01-01T16:30:00.000Z | 2024-01-01T17:00:00.000Z
w_7 | 2024-01-01T16:30:00.000Z | 2024-01-01T17:00:00.000Z