## Verification Report
Planning Validation Report
Status | ✅ PASS
Timestamp | 2025-12-18T09:00:38.036Z
Stats
Total Assignments | 42
Valid Assignments | 42
Invalid Assignments | 0
Constraint Checks | Status | Violations
Hard: Min Workers | PASS | 0
Hard: Max Workers | PASS | 0
Hard: Skills | PASS | 0
Hard: Dependencies | PASS | 0
Hard: Double Booking | PASS | 0

## Assignments
Task | TaskId | Worker | Start | End
Baffels and Blown In Insulation | t_2 | w_10 | 2024-01-01T14:00:00.000Z | 2024-01-01T16:30:00.000Z
Baffels and Blown In Insulation | t_2 | w_7 | 2024-01-01T14:00:00.000Z | 2024-01-01T17:00:00.000Z
Ceiling Rim Insulation | t_3 | w_6 | 2024-01-01T07:00:00.000Z | 2024-01-01T09:00:00.000Z
Ceiling Rim Insulation | t_3 | w_7 | 2024-01-01T07:00:00.000Z | 2024-01-01T09:00:00.000Z
Complete Drywall Back Panel | t_4 | w_1 | 2024-01-01T09:30:00.000Z | 2024-01-01T13:00:00.000Z
Complete Drywall Back Panel | t_4 | w_11 | 2024-01-01T09:30:00.000Z | 2024-01-01T13:30:00.000Z
Complete Drywall Back Panel | t_4 | w_2 | 2024-01-01T09:30:00.000Z | 2024-01-01T13:00:00.000Z
Complete Drywall Back Panel | t_4 | w_8 | 2024-01-01T11:00:00.000Z | 2024-01-01T13:30:00.000Z
Complete Exterior Fire Wall | t_7 | w_1 | 2024-01-01T07:00:00.000Z | 2024-01-01T09:30:00.000Z
Complete Exterior Fire Wall | t_7 | w_11 | 2024-01-01T07:00:00.000Z | 2024-01-01T09:30:00.000Z
Complete Exterior Fire Wall | t_7 | w_2 | 2024-01-01T07:00:00.000Z | 2024-01-01T09:30:00.000Z
Complete Exterior Fire Wall | t_7 | w_3 | 2024-01-01T07:00:00.000Z | 2024-01-01T09:30:00.000Z
Complete Exterior OSB | t_5 | w_3 | 2024-01-01T09:30:00.000Z | 2024-01-01T14:30:00.000Z
Complete Exterior OSB | t_5 | w_4 | 2024-01-01T09:30:00.000Z | 2024-01-01T14:30:00.000Z
Complete Exterior OSB | t_5 | w_5 | 2024-01-01T09:30:00.000Z | 2024-01-01T14:30:00.000Z
Complete Exterior OSB | t_5 | w_6 | 2024-01-01T09:30:00.000Z | 2024-01-01T14:30:00.000Z
Complete Exterior R-Max | t_10 | w_2 | 2024-01-01T13:00:00.000Z | 2024-01-01T17:00:00.000Z
Complete Exterior R-Max | t_10 | w_8 | 2024-01-01T13:30:00.000Z | 2024-01-01T17:00:00.000Z
Complete Exterior R-Max | t_10 | w_9 | 2024-01-01T14:00:00.000Z | 2024-01-01T17:00:00.000Z
Complete Roof 5/8 OSB | t_6 | w_6 | 2024-01-01T09:00:00.000Z | 2024-01-01T09:30:00.000Z
Complete Roof 5/8 OSB | t_6 | w_7 | 2024-01-01T09:00:00.000Z | 2024-01-01T14:00:00.000Z
Complete Roof 5/8 OSB | t_6 | w_10 | 2024-01-01T11:00:00.000Z | 2024-01-01T14:00:00.000Z
Complete Roof 5/8 OSB | t_6 | w_9 | 2024-01-01T11:00:00.000Z | 2024-01-01T14:00:00.000Z
Complete Roof 5/8 OSB | t_6 | w_1 | 2024-01-01T13:00:00.000Z | 2024-01-01T14:30:00.000Z
Final sand of drywall | t_11 | w_14 | 2024-01-01T11:00:00.000Z | 2024-01-01T13:00:00.000Z
Interior Tape / Mud 1st Coat | t_8 | w_10 | 2024-01-01T07:00:00.000Z | 2024-01-01T11:00:00.000Z
Interior Tape / Mud 1st Coat | t_8 | w_12 | 2024-01-01T07:00:00.000Z | 2024-01-01T11:30:00.000Z
Interior Tape / Mud 1st Coat | t_8 | w_13 | 2024-01-01T07:00:00.000Z | 2024-01-01T11:30:00.000Z
Interior Tape / Mud 1st Coat | t_8 | w_14 | 2024-01-01T07:00:00.000Z | 2024-01-01T11:00:00.000Z
Interior Tape / Mud 1st Coat | t_8 | w_15 | 2024-01-01T07:00:00.000Z | 2024-01-01T11:00:00.000Z
Interior Tape / Mud 1st Coat | t_8 | w_16 | 2024-01-01T07:00:00.000Z | 2024-01-01T11:00:00.000Z
Interior Tape / Mud 1st Coat | t_8 | w_8 | 2024-01-01T07:00:00.000Z | 2024-01-01T11:00:00.000Z
Interior Tape / Mud 1st Coat | t_8 | w_9 | 2024-01-01T07:00:00.000Z | 2024-01-01T11:00:00.000Z
Interior Tape / Mud 2nd Coat | t_9 | w_12 | 2024-01-01T11:30:00.000Z | 2024-01-01T15:30:00.000Z
Interior Tape / Mud 2nd Coat | t_9 | w_13 | 2024-01-01T11:30:00.000Z | 2024-01-01T15:30:00.000Z
Interior Tape / Mud 2nd Coat | t_9 | w_15 | 2024-01-01T11:30:00.000Z | 2024-01-01T15:30:00.000Z
Interior Tape / Mud 2nd Coat | t_9 | w_16 | 2024-01-01T11:30:00.000Z | 2024-01-01T15:30:00.000Z
Tape and install windows | t_12 | w_4 | 2024-01-01T14:30:00.000Z | 2024-01-01T17:00:00.000Z
Tape and install windows | t_12 | w_5 | 2024-01-01T14:30:00.000Z | 2024-01-01T16:45:00.000Z
Tape and install windows | t_12 | w_6 | 2024-01-01T14:30:00.000Z | 2024-01-01T15:00:00.000Z
Wall Batt insulation | t_1 | w_4 | 2024-01-01T07:00:00.000Z | 2024-01-01T09:30:00.000Z
Wall Batt insulation | t_1 | w_5 | 2024-01-01T07:00:00.000Z | 2024-01-01T09:30:00.000Z

## Completion Status
Task | TaskId | DoneHours | TotalHours | Progress | Status
Wall Batt insulation | t_1 | 5.00 | 5.00 | 100% | ✅ Complete
Baffels and Blown In Insulation | t_2 | 5.50 | 5.50 | 100% | ✅ Complete
Ceiling Rim Insulation | t_3 | 4.00 | 4.00 | 100% | ✅ Complete
Complete Drywall Back Panel | t_4 | 13.50 | 13.50 | 100% | ✅ Complete
Complete Exterior OSB | t_5 | 20.00 | 20.00 | 100% | ✅ Complete
Complete Roof 5/8 OSB | t_6 | 13.00 | 13.00 | 100% | ✅ Complete
Complete Exterior Fire Wall | t_7 | 10.00 | 10.00 | 100% | ✅ Complete
Interior Tape / Mud 1st Coat | t_8 | 33.00 | 33.00 | 100% | ✅ Complete
Interior Tape / Mud 2nd Coat | t_9 | 16.00 | 16.00 | 100% | ✅ Complete
Complete Exterior R-Max | t_10 | 10.50 | 10.50 | 100% | ✅ Complete
Final sand of drywall | t_11 | 2.00 | 2.00 | 100% | ✅ Complete
Tape and install windows | t_12 | 5.25 | 5.25 | 100% | ✅ Complete

## Idle Workers
Worker | Start | End
w_15 | 2024-01-01T11:00:00.000Z | 2024-01-01T11:30:00.000Z
w_16 | 2024-01-01T11:00:00.000Z | 2024-01-01T11:30:00.000Z
w_14 | 2024-01-01T13:00:00.000Z | 2024-01-01T17:00:00.000Z
w_11 | 2024-01-01T13:30:00.000Z | 2024-01-01T17:00:00.000Z
w_1 | 2024-01-01T14:30:00.000Z | 2024-01-01T17:00:00.000Z
w_3 | 2024-01-01T14:30:00.000Z | 2024-01-01T17:00:00.000Z
w_6 | 2024-01-01T15:00:00.000Z | 2024-01-01T17:00:00.000Z
w_12 | 2024-01-01T15:30:00.000Z | 2024-01-01T17:00:00.000Z
w_13 | 2024-01-01T15:30:00.000Z | 2024-01-01T17:00:00.000Z
w_15 | 2024-01-01T15:30:00.000Z | 2024-01-01T17:00:00.000Z
w_16 | 2024-01-01T15:30:00.000Z | 2024-01-01T17:00:00.000Z
w_10 | 2024-01-01T16:30:00.000Z | 2024-01-01T17:00:00.000Z