## Verification Report
Planning Validation Report
Status | ✅ PASS
Timestamp | 2026-01-07T21:56:07.376Z
Stats
Total Assignments | 22
Valid Assignments | 22
Invalid Assignments | 0
Constraint Checks | Status | Violations
Hard: Min Workers | PASS | 0
Hard: Max Workers | PASS | 0
Hard: Dependencies | PASS | 0
Hard: Double Booking | PASS | 0

## Assignments
Task | TaskId | Worker | Start | End
Fire Tape Fire Walls | t_4 | w_6 | 2024-01-01T10:30:00.000Z | 2024-01-01T11:00:00.000Z
Fire Tape Fire Walls | t_4 | w_7 | 2024-01-01T10:30:00.000Z | 2024-01-01T11:00:00.000Z
Fire Tape Fire Walls | t_4 | w_5 | 2024-01-01T11:00:00.000Z | 2024-01-01T14:30:00.000Z
Fire Tape Fire Walls | t_4 | w_9 | 2024-01-01T13:00:00.000Z | 2024-01-01T14:30:00.000Z
Floor System Completion | t_2 | w_3 | 2024-01-01T09:00:00.000Z | 2024-01-01T11:00:00.000Z
Floor System Completion | t_2 | w_8 | 2024-01-01T09:00:00.000Z | 2024-01-01T13:30:00.000Z
Floor System Completion | t_2 | w_9 | 2024-01-01T09:00:00.000Z | 2024-01-01T13:00:00.000Z
Floor System Completion | t_2 | w_1 | 2024-01-01T10:30:00.000Z | 2024-01-01T13:30:00.000Z
Floor System Completion | t_2 | w_4 | 2024-01-01T11:00:00.000Z | 2024-01-01T13:30:00.000Z
Install Walls on Floor | t_5 | w_2 | 2024-01-01T11:00:00.000Z | 2024-01-01T17:00:00.000Z
Install Walls on Floor | t_5 | w_3 | 2024-01-01T11:00:00.000Z | 2024-01-01T17:00:00.000Z
Install Walls on Floor | t_5 | w_6 | 2024-01-01T11:00:00.000Z | 2024-01-01T17:00:00.000Z
Install Walls on Floor | t_5 | w_7 | 2024-01-01T11:00:00.000Z | 2024-01-01T17:00:00.000Z
Layout Floor System | t_1 | w_3 | 2024-01-01T07:00:00.000Z | 2024-01-01T09:00:00.000Z
Layout Floor System | t_1 | w_8 | 2024-01-01T07:00:00.000Z | 2024-01-01T09:00:00.000Z
Layout Floor System | t_1 | w_9 | 2024-01-01T07:00:00.000Z | 2024-01-01T09:00:00.000Z
Wall Building | t_3 | w_1 | 2024-01-01T07:00:00.000Z | 2024-01-01T10:30:00.000Z
Wall Building | t_3 | w_2 | 2024-01-01T07:00:00.000Z | 2024-01-01T10:30:00.000Z
Wall Building | t_3 | w_4 | 2024-01-01T07:00:00.000Z | 2024-01-01T11:00:00.000Z
Wall Building | t_3 | w_5 | 2024-01-01T07:00:00.000Z | 2024-01-01T11:00:00.000Z
Wall Building | t_3 | w_6 | 2024-01-01T07:00:00.000Z | 2024-01-01T10:30:00.000Z
Wall Building | t_3 | w_7 | 2024-01-01T07:00:00.000Z | 2024-01-01T10:30:00.000Z

## Completion Status
Task | TaskId | DoneHours | TotalHours | Progress | Status
Layout Floor System | t_1 | 6.00 | 6.00 | 100% | ✅ Complete
Floor System Completion | t_2 | 16.00 | 16.00 | 100% | ✅ Complete
Wall Building | t_3 | 22.00 | 22.00 | 100% | ✅ Complete
Fire Tape Fire Walls | t_4 | 6.00 | 6.00 | 100% | ✅ Complete
Install Walls on Floor | t_5 | 24.00 | 25.50 | 94% | 🚧 In Progress

## Idle Workers
Worker | Start | End
w_2 | 2024-01-01T10:30:00.000Z | 2024-01-01T11:00:00.000Z
w_1 | 2024-01-01T13:30:00.000Z | 2024-01-01T17:00:00.000Z
w_4 | 2024-01-01T13:30:00.000Z | 2024-01-01T17:00:00.000Z
w_8 | 2024-01-01T13:30:00.000Z | 2024-01-01T17:00:00.000Z
w_5 | 2024-01-01T14:30:00.000Z | 2024-01-01T17:00:00.000Z
w_9 | 2024-01-01T14:30:00.000Z | 2024-01-01T17:00:00.000Z