## Verification Report
Planning Validation Report
Status | ❌ FAIL
Timestamp | 2025-12-12T23:23:33.850Z
Stats
Total Assignments | 93
Valid Assignments | 92
Invalid Assignments | 1
Constraint Checks | Status | Violations
Hard: Min Workers | FAIL | 1
Hard: Max Workers | PASS | 0
Hard: Skills | PASS | 0
Hard: Dependencies | PASS | 0
Hard: Double Booking | PASS | 0
>>> Min Workers Details
[15:30-17:00] Neudys Perez Santana -> Baffels and Blown In Insulation: Below Min (1 < 2)

## Assignments
Task | TaskId | Worker | Start | End
Baffels and Blown In Insulation | t_2 | w_10 | 2024-01-01T14:00:00.000Z | 2024-01-01T17:00:00.000Z
Baffels and Blown In Insulation | t_2 | w_9 | 2024-01-01T14:00:00.000Z | 2024-01-01T15:30:00.000Z
Baffels and Blown In Insulation | t_2 | w_4 | 2024-01-01T15:30:00.000Z | 2024-01-01T17:00:00.000Z
Ceiling Rim Insulation | t_3 | w_3 | 2024-01-01T10:00:00.000Z | 2024-01-01T10:30:00.000Z
Ceiling Rim Insulation | t_3 | w_4 | 2024-01-01T10:30:00.000Z | 2024-01-01T11:00:00.000Z
Ceiling Rim Insulation | t_3 | w_5 | 2024-01-01T10:30:00.000Z | 2024-01-01T11:00:00.000Z
Ceiling Rim Insulation | t_3 | w_6 | 2024-01-01T10:30:00.000Z | 2024-01-01T11:00:00.000Z
Ceiling Rim Insulation | t_3 | w_7 | 2024-01-01T10:30:00.000Z | 2024-01-01T11:00:00.000Z
Ceiling Rim Insulation | t_3 | w_4 | 2024-01-01T12:00:00.000Z | 2024-01-01T12:30:00.000Z
Ceiling Rim Insulation | t_3 | w_5 | 2024-01-01T12:00:00.000Z | 2024-01-01T12:30:00.000Z
Ceiling Rim Insulation | t_3 | w_6 | 2024-01-01T12:00:00.000Z | 2024-01-01T12:30:00.000Z
Ceiling Rim Insulation | t_3 | w_7 | 2024-01-01T12:00:00.000Z | 2024-01-01T12:30:00.000Z
Complete Drywall Back Panel | t_4 | w_1 | 2024-01-01T15:30:00.000Z | 2024-01-01T17:00:00.000Z
Complete Drywall Back Panel | t_4 | w_11 | 2024-01-01T15:30:00.000Z | 2024-01-01T17:00:00.000Z
Complete Drywall Back Panel | t_4 | w_12 | 2024-01-01T15:30:00.000Z | 2024-01-01T17:00:00.000Z
Complete Drywall Back Panel | t_4 | w_14 | 2024-01-01T15:30:00.000Z | 2024-01-01T17:00:00.000Z
Complete Drywall Back Panel | t_4 | w_2 | 2024-01-01T15:30:00.000Z | 2024-01-01T17:00:00.000Z
Complete Drywall Back Panel | t_4 | w_3 | 2024-01-01T15:30:00.000Z | 2024-01-01T17:00:00.000Z
Complete Drywall Back Panel | t_4 | w_8 | 2024-01-01T15:30:00.000Z | 2024-01-01T17:00:00.000Z
Complete Drywall Back Panel | t_4 | w_9 | 2024-01-01T15:30:00.000Z | 2024-01-01T17:00:00.000Z
Complete Exterior Fire Wall | t_7 | w_1 | 2024-01-01T08:30:00.000Z | 2024-01-01T10:00:00.000Z
Complete Exterior Fire Wall | t_7 | w_11 | 2024-01-01T08:30:00.000Z | 2024-01-01T10:00:00.000Z
Complete Exterior Fire Wall | t_7 | w_2 | 2024-01-01T08:30:00.000Z | 2024-01-01T10:00:00.000Z
Complete Exterior Fire Wall | t_7 | w_3 | 2024-01-01T08:30:00.000Z | 2024-01-01T10:00:00.000Z
Complete Exterior Fire Wall | t_7 | w_11 | 2024-01-01T10:30:00.000Z | 2024-01-01T11:00:00.000Z
Complete Exterior Fire Wall | t_7 | w_3 | 2024-01-01T10:30:00.000Z | 2024-01-01T11:00:00.000Z
Complete Exterior Fire Wall | t_7 | w_11 | 2024-01-01T11:30:00.000Z | 2024-01-01T12:30:00.000Z
Complete Exterior Fire Wall | t_7 | w_3 | 2024-01-01T11:30:00.000Z | 2024-01-01T12:30:00.000Z
Complete Exterior Fire Wall | t_7 | w_10 | 2024-01-01T12:00:00.000Z | 2024-01-01T12:30:00.000Z
Complete Exterior Fire Wall | t_7 | w_12 | 2024-01-01T12:00:00.000Z | 2024-01-01T12:30:00.000Z
Complete Exterior Fire Wall | t_7 | w_13 | 2024-01-01T12:00:00.000Z | 2024-01-01T12:30:00.000Z
Complete Exterior Fire Wall | t_7 | w_14 | 2024-01-01T12:00:00.000Z | 2024-01-01T12:30:00.000Z
Complete Exterior Fire Wall | t_7 | w_8 | 2024-01-01T12:00:00.000Z | 2024-01-01T12:30:00.000Z
Complete Exterior Fire Wall | t_7 | w_9 | 2024-01-01T12:00:00.000Z | 2024-01-01T12:30:00.000Z
Complete Exterior OSB | t_5 | w_1 | 2024-01-01T12:30:00.000Z | 2024-01-01T15:00:00.000Z
Complete Exterior OSB | t_5 | w_2 | 2024-01-01T12:30:00.000Z | 2024-01-01T15:00:00.000Z
Complete Exterior OSB | t_5 | w_3 | 2024-01-01T12:30:00.000Z | 2024-01-01T15:00:00.000Z
Complete Exterior OSB | t_5 | w_4 | 2024-01-01T12:30:00.000Z | 2024-01-01T15:00:00.000Z
Complete Exterior OSB | t_5 | w_5 | 2024-01-01T12:30:00.000Z | 2024-01-01T15:00:00.000Z
Complete Exterior OSB | t_5 | w_6 | 2024-01-01T12:30:00.000Z | 2024-01-01T15:00:00.000Z
Complete Exterior OSB | t_5 | w_7 | 2024-01-01T12:30:00.000Z | 2024-01-01T15:00:00.000Z
Complete Exterior OSB | t_5 | w_8 | 2024-01-01T12:30:00.000Z | 2024-01-01T15:00:00.000Z
Complete Roof 5/8 OSB | t_6 | w_1 | 2024-01-01T08:00:00.000Z | 2024-01-01T08:30:00.000Z
Complete Roof 5/8 OSB | t_6 | w_2 | 2024-01-01T08:00:00.000Z | 2024-01-01T08:30:00.000Z
Complete Roof 5/8 OSB | t_6 | w_3 | 2024-01-01T08:00:00.000Z | 2024-01-01T08:30:00.000Z
Complete Roof 5/8 OSB | t_6 | w_4 | 2024-01-01T08:00:00.000Z | 2024-01-01T10:00:00.000Z
Complete Roof 5/8 OSB | t_6 | w_5 | 2024-01-01T08:00:00.000Z | 2024-01-01T10:00:00.000Z
Complete Roof 5/8 OSB | t_6 | w_6 | 2024-01-01T08:00:00.000Z | 2024-01-01T10:00:00.000Z
Complete Roof 5/8 OSB | t_6 | w_7 | 2024-01-01T08:00:00.000Z | 2024-01-01T10:00:00.000Z
Complete Roof 5/8 OSB | t_6 | w_1 | 2024-01-01T11:00:00.000Z | 2024-01-01T11:30:00.000Z
Complete Roof 5/8 OSB | t_6 | w_2 | 2024-01-01T11:00:00.000Z | 2024-01-01T11:30:00.000Z
Complete Roof 5/8 OSB | t_6 | w_3 | 2024-01-01T11:00:00.000Z | 2024-01-01T11:30:00.000Z
Complete Roof 5/8 OSB | t_6 | w_4 | 2024-01-01T11:00:00.000Z | 2024-01-01T11:30:00.000Z
Complete Roof 5/8 OSB | t_6 | w_5 | 2024-01-01T11:00:00.000Z | 2024-01-01T11:30:00.000Z
Complete Roof 5/8 OSB | t_6 | w_6 | 2024-01-01T11:00:00.000Z | 2024-01-01T11:30:00.000Z
Complete Roof 5/8 OSB | t_6 | w_7 | 2024-01-01T11:00:00.000Z | 2024-01-01T11:30:00.000Z
Final sand of drywall | t_11 | w_11 | 2024-01-01T08:00:00.000Z | 2024-01-01T08:30:00.000Z
Final sand of drywall | t_11 | w_11 | 2024-01-01T10:00:00.000Z | 2024-01-01T10:30:00.000Z
Final sand of drywall | t_11 | w_11 | 2024-01-01T11:00:00.000Z | 2024-01-01T11:30:00.000Z
Interior Tape / Mud 1st Coat | t_8 | w_10 | 2024-01-01T08:00:00.000Z | 2024-01-01T12:00:00.000Z
Interior Tape / Mud 1st Coat | t_8 | w_12 | 2024-01-01T08:00:00.000Z | 2024-01-01T12:00:00.000Z
Interior Tape / Mud 1st Coat | t_8 | w_13 | 2024-01-01T08:00:00.000Z | 2024-01-01T12:00:00.000Z
Interior Tape / Mud 1st Coat | t_8 | w_14 | 2024-01-01T08:00:00.000Z | 2024-01-01T12:00:00.000Z
Interior Tape / Mud 1st Coat | t_8 | w_15 | 2024-01-01T08:00:00.000Z | 2024-01-01T12:30:00.000Z
Interior Tape / Mud 1st Coat | t_8 | w_16 | 2024-01-01T08:00:00.000Z | 2024-01-01T12:30:00.000Z
Interior Tape / Mud 1st Coat | t_8 | w_8 | 2024-01-01T08:00:00.000Z | 2024-01-01T12:00:00.000Z
Interior Tape / Mud 1st Coat | t_8 | w_9 | 2024-01-01T08:00:00.000Z | 2024-01-01T12:00:00.000Z
Interior Tape / Mud 2nd Coat | t_9 | w_10 | 2024-01-01T12:30:00.000Z | 2024-01-01T14:00:00.000Z
Interior Tape / Mud 2nd Coat | t_9 | w_11 | 2024-01-01T12:30:00.000Z | 2024-01-01T15:00:00.000Z
Interior Tape / Mud 2nd Coat | t_9 | w_12 | 2024-01-01T12:30:00.000Z | 2024-01-01T15:00:00.000Z
Interior Tape / Mud 2nd Coat | t_9 | w_13 | 2024-01-01T12:30:00.000Z | 2024-01-01T15:00:00.000Z
Interior Tape / Mud 2nd Coat | t_9 | w_14 | 2024-01-01T12:30:00.000Z | 2024-01-01T15:00:00.000Z
Interior Tape / Mud 2nd Coat | t_9 | w_15 | 2024-01-01T12:30:00.000Z | 2024-01-01T15:00:00.000Z
Interior Tape / Mud 2nd Coat | t_9 | w_16 | 2024-01-01T12:30:00.000Z | 2024-01-01T15:00:00.000Z
Interior Tape / Mud 2nd Coat | t_9 | w_9 | 2024-01-01T12:30:00.000Z | 2024-01-01T14:00:00.000Z
Tape and install windows | t_12 | w_4 | 2024-01-01T10:00:00.000Z | 2024-01-01T10:30:00.000Z
Tape and install windows | t_12 | w_5 | 2024-01-01T10:00:00.000Z | 2024-01-01T10:30:00.000Z
Tape and install windows | t_12 | w_6 | 2024-01-01T10:00:00.000Z | 2024-01-01T10:30:00.000Z
Tape and install windows | t_12 | w_7 | 2024-01-01T10:00:00.000Z | 2024-01-01T10:30:00.000Z
Tape and install windows | t_12 | w_4 | 2024-01-01T11:30:00.000Z | 2024-01-01T12:00:00.000Z
Tape and install windows | t_12 | w_5 | 2024-01-01T11:30:00.000Z | 2024-01-01T12:00:00.000Z
Tape and install windows | t_12 | w_6 | 2024-01-01T11:30:00.000Z | 2024-01-01T12:00:00.000Z
Tape and install windows | t_12 | w_7 | 2024-01-01T11:30:00.000Z | 2024-01-01T12:00:00.000Z
Tape and install windows | t_12 | w_4 | 2024-01-01T15:00:00.000Z | 2024-01-01T15:30:00.000Z
Tape and install windows | t_12 | w_5 | 2024-01-01T15:00:00.000Z | 2024-01-01T15:30:00.000Z
Tape and install windows | t_12 | w_6 | 2024-01-01T15:00:00.000Z | 2024-01-01T15:30:00.000Z
Tape and install windows | t_12 | w_7 | 2024-01-01T15:00:00.000Z | 2024-01-01T15:30:00.000Z
Wall Batt insulation | t_1 | w_1 | 2024-01-01T10:00:00.000Z | 2024-01-01T11:00:00.000Z
Wall Batt insulation | t_1 | w_2 | 2024-01-01T10:00:00.000Z | 2024-01-01T11:00:00.000Z
Wall Batt insulation | t_1 | w_1 | 2024-01-01T11:30:00.000Z | 2024-01-01T12:30:00.000Z
Wall Batt insulation | t_1 | w_2 | 2024-01-01T11:30:00.000Z | 2024-01-01T12:30:00.000Z
Wall Batt insulation | t_1 | w_1 | 2024-01-01T15:00:00.000Z | 2024-01-01T15:30:00.000Z
Wall Batt insulation | t_1 | w_2 | 2024-01-01T15:00:00.000Z | 2024-01-01T15:30:00.000Z

## Completion Status
Task | TaskId | DoneHours | TotalHours | Progress | Status
Wall Batt insulation | t_1 | 5.00 | 5.00 | 100% | ✅ Complete
Baffels and Blown In Insulation | t_2 | 6.00 | 5.50 | 109% | ✅ Complete
Ceiling Rim Insulation | t_3 | 4.50 | 4.00 | 113% | ✅ Complete
Complete Drywall Back Panel | t_4 | 12.00 | 13.50 | 89% | 🚧 In Progress
Complete Exterior OSB | t_5 | 20.00 | 20.00 | 100% | ✅ Complete
Complete Roof 5/8 OSB | t_6 | 13.00 | 13.00 | 100% | ✅ Complete
Complete Exterior Fire Wall | t_7 | 12.00 | 10.00 | 120% | ✅ Complete
Interior Tape / Mud 1st Coat | t_8 | 33.00 | 33.00 | 100% | ✅ Complete
Interior Tape / Mud 2nd Coat | t_9 | 18.00 | 16.00 | 113% | ✅ Complete
Complete Exterior R-Max | t_10 | 0.00 | 10.50 | 0% | 🛑 Not Started
Final sand of drywall | t_11 | 1.50 | 2.00 | 75% | 🚧 In Progress
Tape and install windows | t_12 | 6.00 | 5.25 | 114% | ✅ Complete

## Idle Workers
Worker | Start | End
w_11 | 2024-01-01T15:00:00.000Z | 2024-01-01T15:30:00.000Z
w_12 | 2024-01-01T15:00:00.000Z | 2024-01-01T15:30:00.000Z
w_13 | 2024-01-01T15:00:00.000Z | 2024-01-01T17:00:00.000Z
w_14 | 2024-01-01T15:00:00.000Z | 2024-01-01T15:30:00.000Z
w_15 | 2024-01-01T15:00:00.000Z | 2024-01-01T17:00:00.000Z
w_16 | 2024-01-01T15:00:00.000Z | 2024-01-01T17:00:00.000Z
w_3 | 2024-01-01T15:00:00.000Z | 2024-01-01T15:30:00.000Z
w_8 | 2024-01-01T15:00:00.000Z | 2024-01-01T15:30:00.000Z
w_5 | 2024-01-01T15:30:00.000Z | 2024-01-01T17:00:00.000Z
w_6 | 2024-01-01T15:30:00.000Z | 2024-01-01T17:00:00.000Z
w_7 | 2024-01-01T15:30:00.000Z | 2024-01-01T17:00:00.000Z

## Task Idle Periods
Task | TaskId | Start | End
Wall Batt insulation | t_1 | 2024-01-01T08:00:00.000Z | 2024-01-01T10:00:00.000Z
Complete Exterior R-Max | t_10 | 2024-01-01T08:00:00.000Z | 2024-01-01T17:00:00.000Z
Tape and install windows | t_12 | 2024-01-01T08:00:00.000Z | 2024-01-01T10:00:00.000Z
Ceiling Rim Insulation | t_3 | 2024-01-01T08:00:00.000Z | 2024-01-01T10:00:00.000Z
Complete Exterior Fire Wall | t_7 | 2024-01-01T08:00:00.000Z | 2024-01-01T08:30:00.000Z
Final sand of drywall | t_11 | 2024-01-01T08:30:00.000Z | 2024-01-01T10:00:00.000Z
Complete Roof 5/8 OSB | t_6 | 2024-01-01T10:00:00.000Z | 2024-01-01T11:00:00.000Z
Complete Exterior Fire Wall | t_7 | 2024-01-01T10:00:00.000Z | 2024-01-01T10:30:00.000Z
Final sand of drywall | t_11 | 2024-01-01T10:30:00.000Z | 2024-01-01T11:00:00.000Z
Tape and install windows | t_12 | 2024-01-01T10:30:00.000Z | 2024-01-01T11:30:00.000Z
Wall Batt insulation | t_1 | 2024-01-01T11:00:00.000Z | 2024-01-01T11:30:00.000Z
Ceiling Rim Insulation | t_3 | 2024-01-01T11:00:00.000Z | 2024-01-01T12:00:00.000Z
Complete Exterior Fire Wall | t_7 | 2024-01-01T11:00:00.000Z | 2024-01-01T11:30:00.000Z
Final sand of drywall | t_11 | 2024-01-01T11:30:00.000Z | 2024-01-01T17:00:00.000Z
Tape and install windows | t_12 | 2024-01-01T12:00:00.000Z | 2024-01-01T15:00:00.000Z
Wall Batt insulation | t_1 | 2024-01-01T12:30:00.000Z | 2024-01-01T15:00:00.000Z
Baffels and Blown In Insulation | t_2 | 2024-01-01T12:30:00.000Z | 2024-01-01T14:00:00.000Z